## Loops with no Instruments
Loop Number | IS_IN_MATRIX_SHEET | LOOP_NUMBER_ONLY | NUMBER_IS_IN_JACOBS_LIST | NUMBER_IS_IN_MATRIX_SHEET | Description | Loop Check Status | Target Loop Check Date | Instrument Tags | Company Providing Loop | PIDs | Location Plans | Loop Drawings | Notes | Junction Boxes | Area List | Responsible Company | Loop Folder Received
AI-20626 | FALSE | 20626 | FALSE | FALSE | U/F EXCESS HCI REMOVAL CONDUCTIVITY ANALYZER | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
CTA-210216 | FALSE | 210216 | TRUE | FALSE | S/G COMP RECYCLE 1 PLC POWER SUPPLY ALARM | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
CTA-210217 | FALSE | 210217 | TRUE | FALSE | S/G COMP RECYCLE 2 PLC POWER SUPPLY ALARM | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
CTA-210230 | FALSE | 210230 | TRUE | FALSE | S/G COMP BENTLY NEVADA COMMON TROUBLE ALARM | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
CTA-210232 | FALSE | 210232 | TRUE | FALSE | S/G COMP BENTLY NEVADA COMMON TROUBLE ALARM | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FC-20108C | FALSE | 20108C | FALSE | FALSE | 2ND STAGE FEED | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
FC-210015 | FALSE | 210015 | TRUE | FALSE | M/U COMP 1ST STAGE NDE PRIMARY SEAL GAS FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FC-210024 | FALSE | 210024 | TRUE | FALSE | M/U COMP 2ND STAGE NDE PRIMARY SEAL GAS FLOW | Complete but Requires Further Action. | 2015-12-04 |  | JACOBS |  |  |  | NEEDS HT |  |  |  | FALSE
FC-210033 | FALSE | 210033 | TRUE | FALSE | M/U COMP 3RD STAGE NDE PRIMARY SEAL GAS FLOW | Complete but Requires Further Action. | 2015-12-03 |  | JACOBS |  |  |  | NEEDS HT |  |  |  | FALSE
FC-210051 | FALSE | 210051 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR DE PRIMARY SEAL GAS | Complete but Requires Further Action. | 2016-01-08 |  | JACOBS |  |  |  | Air tubing not complete |  |  |  | FALSE
FC-210069 | FALSE | 210069 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR DE PRIMARY SEAL GAS | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FI-20101AB | FALSE | 20101AB | FALSE | FALSE | ISO 1ST STAGE FEED | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
FI-98138 | FALSE | 98138 | FALSE | FALSE | LP COND FR AROMATICS | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
FIT-210017 | FALSE | 210017 | TRUE | FALSE | M/U COMP 1ST STAGE DE SECONDARY SEAL GAS SUPPLY FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210018 | FALSE | 210018 | TRUE | FALSE | M/U COMP 1ST STAGE NDE SECONDARY SEAL GAS SUPPLY FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210022A,B,C | FALSE | 210022A,B,C | FALSE | FALSE | M/U COMP 1ST STAGE DE PRIMARY SEAL LEAKAGE FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210023A,B,C | FALSE | 210023A,B,C | FALSE | FALSE | M/U COMP 1ST STAGE NDE PRIMARY SEAL LEAKAGE FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210026 | FALSE | 210026 | TRUE | FALSE | M/U COMP 2ND STAGE DE SECONDARY SEAL GAS FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210027 | FALSE | 210027 | TRUE | FALSE | M/U COMP 2ND STAGE NDE SECONDARY SEAL GAS FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210031A,B,C | FALSE | 210031A,B,C | FALSE | FALSE | M/U COMP 2ND STAGE DE PRIMARY SEAL LEAKAGE FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210032A,B,C | FALSE | 210032A,B,C | FALSE | FALSE | M/U COMP 2ND STAGE NDE PRIMARY SEAL LEAKAGE FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210035 | FALSE | 210035 | TRUE | FALSE | M/U COMP 3RD STAGE DE SECONDARY SEAL GAS FLOW | Complete - Ready for Startup | 2015-12-03 |  | JACOBS | [7 empty] | FALSE
FIT-210036 | FALSE | 210036 | TRUE | FALSE | M/U COMP 3RD STAGE NDE SECONDARY SEAL GAS FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210040A,B,C | FALSE | 210040A,B,C | FALSE | FALSE | M/U COMP 3RD STAGE DE PRIMARY SEAL LEAKAGE FLOW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
FIT-210041A,B,C | FALSE | 210041A,B,C | FALSE | FALSE | M/U COMP 3RD STAGE NDE PRIMARY SEAL LEAKAGE FLOW | Complete - Ready for Startup | 2015-12-03 |  | JACOBS | [7 empty] | FALSE
FIT-210053 | FALSE | 210053 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR DE SECONDARY SEAL GAS SUPPLY FLOW | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FIT-210054 | FALSE | 210054 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR NDE SECONDARY SEAL GAS SUPPLY FLOW | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FIT-210058 | FALSE | 210058 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR DE PRIMARY SEAL LEAKAGE FLOW XMITTER A, B & C | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FIT-210059 | FALSE | 210059 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR NDE PRIMARY SEAL LEAKAGE FLOW XMITTER A, B & C | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FIT-210071 | FALSE | 210071 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR DE SECONDARY SEAL GAS SUPPLY FLOW | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FIT-210072 | FALSE | 210072 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR NDE SECONDARY SEAL GAS SUPPLY FLOW | Complete - Ready for Startup | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
FIT-210076 | FALSE | 210076 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR DE PRIMARY SEAL LEAKAGE FLOW XMITTER A,B & C | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
FIT-210077 | FALSE | 210077 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR NDE PRIMARY SEAL LEAKAGE FLOW XMITTER A,B & C | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HA-210196 | FALSE | 210196 | FALSE | FALSE | SOUTH SECOND STAGE FEED PUMP MOTOR STATUS | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HS-20064A | FALSE | 20064A | FALSE | FALSE | 1ST STAGE COMPRESSOR PANEL MTD STOP | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-20064AA | FALSE | 20064AA | FALSE | FALSE | 1ST STAGE COMPRESSOR FIELD MOUNTED START | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-20064B | FALSE | 20064B | FALSE | FALSE | 1ST STAGE COMPRESSOR DCS CONSOLE MTD STOP | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-20065A | FALSE | 20065A | FALSE | FALSE | 2ND STAGE COMPRESSOR PANEL MTD STOP | Being Checked | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-20065AA | FALSE | 20065AA | FALSE | FALSE | 2ND STAGE COMPRESSOR FIELD MOUNTED START | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-20065B | FALSE | 20065B | FALSE | FALSE | 2ND STAGE COMPRESSOR DCS CONSOLE MTD STOP | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-20240 | FALSE | 20240 | FALSE | FALSE | M/U COMP SPARE LUBE OIL PUMP, STEAM TURBINE, IN AUTO | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-20366 | FALSE | 20366 | TRUE | FALSE | SPARE LUBE OIL PUMP, STEAM TURBINE, IN AUTO | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-20694 | FALSE | 20694 | FALSE | FALSE | INITATE TEST | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
HS-20697A | FALSE | 20697A | FALSE | FALSE | ISO 2 STAGE DEPRES RESET | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
HS-20712 | FALSE | 20712 | FALSE | FALSE | FEED SURGE DRUM OUTLET | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
HS-20922A | FALSE | 20922A | FALSE | FALSE | ISO NOX SCR PLC PANEL E STOP | Being Checked | 2015-12-15 |  | FIELD | [7 empty] | FALSE
HS-20924A | FALSE | 20924A | FALSE | FALSE | NOX DCS CONSOLE PLC AMMONIA TRIP | Being Checked | 2015-12-15 |  | FIELD | [7 empty] | FALSE
HS-20925 | FALSE | 20925 | FALSE | FALSE | ISO NOX PLC PANEL AMMONIA SKID START | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
HS-20926 | FALSE | 20926 | FALSE | FALSE | ISO NOX SCR MAINTENANCE MODE PERMISSIVE SELECTOR SWITCH | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
HS-210008 | FALSE | 210008 | TRUE | FALSE | M/U COMP 1ST STAGE AMPLIFLOW ENABLE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-210009 | FALSE | 210009 | TRUE | FALSE | M/U COMP 2ND STAGE AMPLIFLOW ENABLE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-210010 | FALSE | 210010 | TRUE | FALSE | M/U COMP 3RD STAGE AMPLIFLOW ENABLE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-210196 | FALSE | 210196 | FALSE | FALSE | SOUTH SECOND STAGE FEED PUMP MOTOR SHUTDOWN | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HS-210197A | FALSE | 210197A | FALSE | FALSE | POWER RECOVERY TURBINE INLET EIV RESET | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HS-210197B | FALSE | 210197B | FALSE | FALSE | POWER RECOVERY TURBINE INLET EIV TRIP | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HS-210198A | FALSE | 210198A | FALSE | FALSE | POWER RECOVERY TURBINE OUTLET EIV RESET | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HS-210198B | FALSE | 210198B | FALSE | FALSE | POWER RECOVERY TURBINE OULET EIV TRIP | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HS-210222 | FALSE | 210222 | TRUE | FALSE | ACK BUTTON | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-210223 | FALSE | 210223 | TRUE | FALSE | RESET BUTTON | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-210224 | FALSE | 210224 | TRUE | FALSE | TEST AUX LUBE PUMP BUTTON | Loop Check Failed | 2016-01-09 |  | JACOBS |  |  |  | DELETED PER AARON SIFERD |  |  |  | FALSE
HS-210225 | FALSE | 210225 | TRUE | FALSE | MAINTENANCE MODE SS | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-210226 | FALSE | 210226 | TRUE | FALSE | ACK BUTTON | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-210227 | FALSE | 210227 | TRUE | FALSE | RESET BUTTON | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-210228 | FALSE | 210228 | TRUE | FALSE | M/U COMP LUBE OIL PUMP HOA IN AUTO | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-210229 | FALSE | 210229 | TRUE | FALSE | MAINTENANCE MODE SS | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
HS-210231 | FALSE | 210231 | TRUE | FALSE | FROM BENTLY NEVADA TRIP BYPASS STATUS | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
HS-210233 | FALSE | 210233 | TRUE | FALSE | 2ND STAGE COMPRESSOR FROM BENTLY NEVADA TRIP BYPASS STATUS | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
HS-210235 | FALSE | 210235 | TRUE | FALSE | 1ST STAGE COMPRESSOR E STOP | Loop Check Failed | 2016-01-09 |  | JACOBS |  |  |  | DELETED PER AARON SIFERD |  |  |  | FALSE
HS-210236 | FALSE | 210236 | TRUE | FALSE | 2ND STAGE COMPRESSOR E STOP | Loop Check Failed | 2016-01-09 |  | JACOBS |  |  |  | DELETED PER AARON SIFERD |  |  |  | FALSE
HS-210237 | FALSE | 210237 | TRUE | FALSE | M/U COMP DGS PANEL MAINTENANCE MODE PERMISSIVE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
HS-210239 | FALSE | 210239 | TRUE | FALSE | LUBE OIL PUMP HOA IN AUTO | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-210239BB | FALSE | 210239BB | FALSE | FALSE | SPARE LUBE OIL PUMP, STEAM TURBINE, IN AUTO | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
HS-210240 | FALSE | 210240 | TRUE | FALSE | TEST AUX PUMP BUTTON | Loop Check Failed | 2016-01-09 |  | JACOBS |  |  |  | DELETED PER AARON SIFERD |  |  |  | FALSE
HS-210246 | FALSE | 210246 | TRUE | FALSE | M/U COMP ACK BUTTON | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
HS-219006 | FALSE | 219006 | TRUE | FALSE | DRY GAS SEAL ALARM RESET | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
HV-210186 | FALSE | 210186 | FALSE | FALSE | SOUTH FIRST STAGE FEED PUMP DISCH MOV | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HV-210195 | FALSE | 210195 | FALSE | FALSE | FEED | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HV-210202 | FALSE | 210202 | FALSE | FALSE |  | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
HV-210204 | FALSE | 210204 | FALSE | FALSE |  | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
LI-210247 | FALSE | 210247 | TRUE | FALSE | M/U COMP PANEL STROBE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
LIT-20541 | FALSE | 20541 | TRUE | FALSE | 2ND STAGE SEAL OIL TANK | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
LIT-210001 | FALSE | 210001 | TRUE | FALSE | M/U COMP CLEANPAC F LEVEL | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
LIT-210043 | FALSE | 210043 | TRUE | FALSE | CLEANPAC F LEVEL | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
LIT-210061 | FALSE | 210061 | TRUE | FALSE | CLEANPAC F LEVEL | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
LSL-20567 | FALSE | 20567 | FALSE | FALSE | FG SCRUBBER PR-164886 | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
PC-91328 | FALSE | 91328 | FALSE | FALSE | 125# STEAM TO 40# STEAM | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
PDIT-20343 | FALSE | 20343 | TRUE | FALSE | M/U COMP LUBE OIL FILTER DIFFERENTIAL FILTER | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PDIT-20383 | FALSE | 20383 | TRUE | FALSE | SEAL OIL DIFFERENTIALS | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PDIT-20384 | FALSE | 20384 | TRUE | FALSE | SEAL OIL 1ST STAGE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PDIT-20385 | FALSE | 20385 | TRUE | FALSE | SEAL OIL FILTER DIFFERENTIAL | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PDIT-210002 | FALSE | 210002 | TRUE | FALSE | M/U COMP CLEANPAC F DIFERENTIAL PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PDIT-210004 | FALSE | 210004 | TRUE | FALSE | M/U COMP SEAL GAS SUPPLY FILTER DIFFERENTIAL PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PDIT-210014 | FALSE | 210014 | TRUE | FALSE | M/U COMP SEPARATION / SECONDARY SEAL GAS FILTER DIFFERENTIAL PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PDIT-210044 | FALSE | 210044 | TRUE | FALSE | CLEANPAC F DIFFERENTIAL PRESSURE | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDIT-210049 | FALSE | 210049 | TRUE | FALSE | SEAL GAS SUPPLY FILTER DIFFERENTIAL PRESSURE TRANSMITTER | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDIT-210050 | FALSE | 210050 | TRUE | FALSE | NITROGEN SUPPLY FILTER DIFFERENTIAL PRESSURE TRANSMITTER | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDIT-210062 | FALSE | 210062 | TRUE | FALSE | CLEANPAC F DIFERENTIAL PRESSURE | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDIT-210067 | FALSE | 210067 | TRUE | FALSE | SEAL GAS SUPPLY FILTER DIFFERENTIAL PRESSURE TRANSMITTER | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDIT-210068 | FALSE | 210068 | TRUE | FALSE | NITROGEN SUPPLY FILTER DIFFERENTIAL PRESSURE TRANSMITTER | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDIT-210247 | FALSE | 210247 | TRUE | FALSE | LUBE OIL FILTER DIFF PRESSURE, TO ONLY ONE OF THE PLC'S | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PDT-20375 | FALSE | 20375 | FALSE | FALSE |  | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PI-20310AB | FALSE | 20310AB | FALSE | FALSE | STAB. FURNACE PILOT GAS A AND B | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
PI-20313A | FALSE | 20313A | FALSE | FALSE | 1ST STG 2ND BD INLT PRES | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
PI-20317 | FALSE | 20317 | TRUE | FALSE | LOW LUBE OIL PRESSURE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PI-20407 | FALSE | 20407 | FALSE | FALSE | M/U COMP STEAM CHEST PRESSURE | Being Checked | 2015-12-14 |  | FIELD | [7 empty] | FALSE
PI-20416 | FALSE | 20416 | TRUE | FALSE | 2ND STAGE DISCHARGE | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PI-210206 | FALSE | 210206 | FALSE | FALSE | POWER RECOVERY TURBINE INLET PRESSURE | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PI-210265AB | FALSE | 210265AB | FALSE | FALSE | LUBE OIL SUPPLY | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PI-210265C | FALSE | 210265C | FALSE | FALSE | LUBE OIL SUPPLY | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PIT-20317A | FALSE | 20317A | FALSE | FALSE | 2ND STAGE COMPRESSOR LUBE OIL PRESSURE TRANSMITTER A | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PIT-20317B | FALSE | 20317B | FALSE | FALSE | 2ND STAGE COMPRESSOR LUBE OIL PRESSURE TRANSMITTER B | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PIT-20339 | FALSE | 20339 | TRUE | FALSE | TURBINE EXHAUST PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-20342 | FALSE | 20342 | TRUE | FALSE | H2 M/U TURBINE STEAM SUPPLY PRESSURE | Complete but Requires Further Action. | 2015-12-04 |  | JACOBS |  |  |  | Field device needs to be retagged |  |  |  | FALSE
PIT-20348 | FALSE | 20348 | TRUE | FALSE | M/U COMP TURBINE PILOT VALVE LUBE OIL PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-20366A | FALSE | 20366A | FALSE | FALSE | LUBE OIL PUMP PRESSURE, CHANGE PSL TO TWO PIT'S | Complete - Ready for Startup | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
PIT-20366B | FALSE | 20366B | FALSE | FALSE | LUBE OIL PUMP PRESSURE, CHANGE PSL TO TWO PIT'S | Complete - Ready for Startup | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
PIT-20390 | FALSE | 20390 | TRUE | FALSE | SEAL OIL 2ND STAGE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PIT-20391 | FALSE | 20391 | TRUE | FALSE | SEAL OIL 1ST STAGE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PIT-20450 | FALSE | 20450 | FALSE | FALSE | M/U LUBE OIL PRESSURE A & B | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210000 | FALSE | 210000 | TRUE | FALSE | 3RD STAGE M/U DISCHARGE GAS PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210011 | FALSE | 210011 | TRUE | FALSE | M/U COMP AMPLIFLOW IST STAGE LEAKAGE LINE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210012 | FALSE | 210012 | TRUE | FALSE | M/U COMP AMPLIFLOW 2ND STAGE LEAKAGE LINE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210013 | FALSE | 210013 | TRUE | FALSE | M/U COMP AMPLIFLOW 3RD STAGE LEAKAGE LINE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210016 | FALSE | 210016 | TRUE | FALSE | M/U COMP 1ST STAGE PRIMARY SEAL GAS PRESSURE | Complete but Requires Further Action. | 2015-12-04 |  | JACOBS |  |  |  | NEEDS HT |  |  |  | FALSE
PIT-210019 | FALSE | 210019 | TRUE | FALSE | M/U COMP 1ST STAGE SEPARATION SEAL GAS PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210020 | FALSE | 210020 | TRUE | FALSE | M/U COMP 1ST STAGE DE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210021 | FALSE | 210021 | TRUE | FALSE | M/U COMP 1ST STAGE NDE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210025 | FALSE | 210025 | TRUE | FALSE | M/U COMP 2ND STAGE PRIMARY SEAL GAS PRESSURE | Complete but Requires Further Action. | 2015-12-04 |  | JACOBS |  |  |  | NEEDS HT |  |  |  | FALSE
PIT-210028 | FALSE | 210028 | TRUE | FALSE | M/U COMP 2ND STAGE SEPARATION SEAL GAS PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210029 | FALSE | 210029 | TRUE | FALSE | M/U COMP 2ND STAGE DE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210030 | FALSE | 210030 | TRUE | FALSE | M/U COMP 2ND STAGE NDE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210034 | FALSE | 210034 | TRUE | FALSE | M/U COMP 3RD STAGE PRIMARY SEAL GAS PRESSURE | Complete but Requires Further Action. | 2015-12-04 |  | JACOBS |  |  |  | NEEDS HT |  |  |  | FALSE
PIT-210037 | FALSE | 210037 | TRUE | FALSE | M/U COMP 3RD STAGE SEPARATION SEAL GAS PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210038 | FALSE | 210038 | TRUE | FALSE | M/U COMP 3RD STAGE DE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210039 | FALSE | 210039 | TRUE | FALSE | M/U COMP 3RD STAGE NDE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
PIT-210042 | FALSE | 210042 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR DISCHARGE GAS PRESSURE | Complete - Ready for Startup | 2016-01-10 |  | JACOBS | [7 empty] | FALSE
PIT-210048 | FALSE | 210048 | TRUE | FALSE | 1ST STAGE AMPLIFLOW PROCESS LEAKAGE TO FLARE | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210052 | FALSE | 210052 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR PRIMARY SEAL GAS PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210055 | FALSE | 210055 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR SEPARATION SEAL GAS PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210056 | FALSE | 210056 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR DE PRIMARY SEAL LEAKAGE PRESSURE | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210057 | FALSE | 210057 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR NDE PRIMARY SEAL LEAKAGE PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210060 | FALSE | 210060 | TRUE | FALSE | 1ST STAGE RECYCLE COMPRESSOR DISCHARGE GAS PRESSURE | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210064 | FALSE | 210064 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR SUCTION PRESSURE | Being Checked |  |  | JACOBS | [7 empty] | FALSE
PIT-210066 | FALSE | 210066 | TRUE | FALSE | 2ND STAGE AMPLIFLOW PROCESS LEAKSGE TO FLARE | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210070 | FALSE | 210070 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR PRIMARY SEAL GAS PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210073 | FALSE | 210073 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR SEPARATION SEAL GAS PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210074 | FALSE | 210074 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR DE PRIMARY SEAL LEAKAGE PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210075 | FALSE | 210075 | TRUE | FALSE | 2ND STAGE RECYCLE COMPRESSOR NDE PRIMARY SEAL LEAKAGE PRESSURE | Complete but Requires Further Action. | 2016-01-11 |  | JACOBS |  |  |  | DCS Range Change |  |  |  | FALSE
PIT-210244A | FALSE | 210244A | FALSE | FALSE | 1ST STAGE COMPRESSOR LUBE OIL PRESSURE TRANSMITTER A | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210244B | FALSE | 210244B | FALSE | FALSE | 1ST STAGE COMPRESSOR LUBE OIL PRESSURE TRANSMITTER B | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210250 | FALSE | 210250 | TRUE | FALSE | 2ND STAGE COMPRESSOR DISCH PRESSURE | Being Checked | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PIT-210258AB | FALSE | 210258AB | FALSE | FALSE | LUBE OIL SUPPLY | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PIT-210258C | FALSE | 210258C | FALSE | FALSE | LUBE OIL SUPPLY | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PIT-210272AB | FALSE | 210272AB | FALSE | FALSE | LUBE OIL SUPPLY | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PIT-210272C | FALSE | 210272C | FALSE | FALSE | LUBE OIL SUPPLY | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
PIT-30361 | FALSE | 30361 | FALSE | FALSE | 2ND STG 2ND BD INLT PRESSURE | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
PSL-210220 | FALSE | 210220 | TRUE | FALSE | PLC PANEL PURGE ALARM | Complete - Ready for Startup | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
PSL-210234 | FALSE | 210234 | TRUE | FALSE | FROM BENTLY NEVADA PANEL PURGE ALARM | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
PY-20340 | FALSE | 20340 | TRUE | FALSE | OUTPUT TO M/U COMP STEAM VALVE FOR TURBINE, AUTO START | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PY-20340A | FALSE | 20340A | FALSE | FALSE | SPARE LUBE OIL PUMP, M/U COMP STEAM TURBINE, PERMISSIVE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
PY-20366 | FALSE | 20366 | TRUE | FALSE | 125# STEAM TO LUBE OIL PUMP | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
ST-20617A/B | FALSE | 20617A/B | FALSE | FALSE | ISO M/U COMPR TURBINE SPEED | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
ST-20617C/D | FALSE | 20617C/D | FALSE | FALSE | MAKE UP COMP RPM | Not Ready for Check |  |  | FIELD | [7 empty] | FALSE
TAD-20008C1 | FALSE | 20008C1 | FALSE | FALSE | ISO STG2 BED3 TOP- | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TAL-210003 | FALSE | 210003 | TRUE | FALSE | M/U COMP SEAL GAS PROCESS TEMPERATURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
TC-210003 | FALSE | 210003 | TRUE | FALSE | M/U COMP SEAL GAS PROCESS TEMPERATURE | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
TC-210045 | FALSE | 210045 | TRUE | FALSE | SEAL GAS PROCESS TEMPERATURE | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
TC-210046 | FALSE | 210046 | TRUE | FALSE | SEAL GAS PROCESS TEMPERATURE | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
TC-210063 | FALSE | 210063 | TRUE | FALSE | SEAL GAS PROCESS TEMPERATURE | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
TD-20012 | FALSE | 20012 | FALSE | FALSE | TEMP DIFF BEDS TOP AND BOTTOM | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TD-20013 | FALSE | 20013 | FALSE | FALSE | TEMP DIFF BEDS TOP AND BOTTOM | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TI-20018 | FALSE | 20018 | FALSE | FALSE | ISO STAGE 1 FEED/FURNACE/REACTOR | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TI-210208 | FALSE | 210208 | FALSE | FALSE | FIRST STAGE FEED PUMP DISCHARGE TEMPERATURE | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
TI-210288 | FALSE | 210288 | FALSE | FALSE | SPLITTER BOTTOMS FEED TEMPERATURE | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
TI-21059 | FALSE | 21059 | FALSE | FALSE | 1ST STG RX AIR CLR PR150564 N OUTLET | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TI-21060 | FALSE | 21060 | FALSE | FALSE | 1ST STG RX AIR CLR PR150564 S OUTLET | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TIT-210221 | FALSE | 210221 | TRUE | FALSE | PLC PANEL TEMPERATURE | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
TSH-20026 | FALSE | 20026 | TRUE | FALSE | FROM BENTLY NEVADA | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
TSH-20341 | FALSE | 20341 | TRUE | FALSE | M/U COMP STANDYBY LUBE OIL COOLER DISCH TEMP | Being Checked | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
TSH-20999 | FALSE | 20999 | FALSE | FALSE | 2ND STG FEED PUMP MOTOR | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TSH-210246 | FALSE | 210246 | TRUE | FALSE | LUBE OIL FILTER DIFF TEMPERATURE, TO ONLY ONE OF THE PLC'S | Being Checked | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
TT-200035 | FALSE | 200035 | FALSE | FALSE | 2ND STG RX OUTLET TEMP TRANSMITTER A & B | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
TT-20087 | FALSE | 20087 | FALSE | FALSE | REACTOR OUTLET TEMPERATURE TRANSMITTER A & B | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
XA-20722 | FALSE | 20722 | FALSE | FALSE | AIC-20722 TROUBLE ALARM | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
XA-210003 | FALSE | 210003 | TRUE | FALSE | M/U COMP HEATER COMMON ALARM | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XA-210045 | FALSE | 210045 | TRUE | FALSE | HEATER COMMON ALARM | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XA-210063 | FALSE | 210063 | TRUE | FALSE | HEATER COMMON ALARM | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XA-210110 | FALSE | 210110 | TRUE | FALSE | M/U COMP PLC CARD AND INSTRUMENT FAILURE COMMON ALARM | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
XA-210252 | FALSE | 210252 | FALSE | FALSE |  | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
XA-210259 | FALSE | 210259 | FALSE | FALSE |  | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
XA-210266 | FALSE | 210266 | FALSE | FALSE |  | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
XA-210273 | FALSE | 210273 | FALSE | FALSE | 2ND STAGE ISO FEED LUBE | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
XI-210008 | FALSE | 210008 | TRUE | FALSE | M/U COMP 1ST STAGE AMPLIFLOW FEEDBACK SENSOR | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XI-210009 | FALSE | 210009 | TRUE | FALSE | M/U COMP 2ND STAGE AMPLIFLOW FEEDBACK SENSOR | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XI-210010 | FALSE | 210010 | TRUE | FALSE | M/U COMP 3RD STAGE AMPLIFLOW FEEDBACK SENSOR | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XI-210047 | FALSE | 210047 | TRUE | FALSE | 1ST STAGE RECYCLE AMPLIFLOW SOLENOID CYCLE FEEDBACK | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XI-210065 | FALSE | 210065 | TRUE | FALSE | 2ND STAGE RECYCLE AMPLIFLOW SOLENOID CYCLE FEEDBACK | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XL-20064A | FALSE | 20064A | FALSE | FALSE | 1ST STAGE COMPRESSOR PANEL MOUNTED START LIGHT | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XL-20064B | FALSE | 20064B | FALSE | FALSE | 1ST STAGE COMPRESSOR PANEL MTD STOP LIGHT | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XL-20065A | FALSE | 20065A | FALSE | FALSE | 2ND STAGE COMPRESSOR PLC START | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XL-20065B | FALSE | 20065B | FALSE | FALSE | 2ND STAGE COMPRESSOR PLC STOP | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XL-20905 | FALSE | 20905 | FALSE | FALSE | PURGE | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
XL-210003A | FALSE | 210003A | FALSE | FALSE | M/U COMP HEATER ON/OFF | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XL-210003B | FALSE | 210003B | FALSE | FALSE | M/U COMP HEATER MODE OPERATION SELECT | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XL-210045A | FALSE | 210045A | FALSE | FALSE | HEATER ON/OFF | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XL-210045B | FALSE | 210045B | FALSE | FALSE | HEATER MODE OPERATION SELECT | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XL-210063A | FALSE | 210063A | FALSE | FALSE | HEATER ON/OFF | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XL-210063B | FALSE | 210063B | FALSE | FALSE | HEATER MODE OPERATION SELECT | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XL-210218 | FALSE | 210218 | TRUE | FALSE | RECYCLE 1 PLC BEACON | Being Checked | 2016-01-11 |  | JACOBS | [7 empty] | FALSE
XL-210219 | FALSE | 210219 | TRUE | FALSE | RECYCLE 2 PLC BEACON | Being Checked | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XL-210225 | FALSE | 210225 | TRUE | FALSE | MAINTENANCE MODE LIGHT | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XL-210229 | FALSE | 210229 | TRUE | FALSE | MAINTENANCE MODE LIGHT | Complete - Ready for Startup | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XL-210237 | FALSE | 210237 | TRUE | FALSE | M/U COMP DGS PANEL MAINTENANCE MODE ENABLED | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XL-210247 | FALSE | 210247 | TRUE | FALSE |  | Complete - Ready for Startup |  |  | JACOBS | [7 empty] | FALSE
XS-20064 | FALSE | 20064 | TRUE | FALSE | 1ST STAGE COMPRESSOR RUN STATUS | Being Checked | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XS-20065 | FALSE | 20065 | TRUE | FALSE | 2ND STAGE COMPRESSOR RUN STATUS | Being Checked | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XS-210111 | FALSE | 210111 | TRUE | FALSE | M/U COMP COMPRESSOR RUN STATUS FROM TRICONEX TO PLC | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XS-210112 | FALSE | 210112 | TRUE | FALSE | M/U COMP LUBE OIL START PERMISSIVE SIGNAL FROM SEAL VIEW | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XS-210228 | FALSE | 210228 | TRUE | FALSE | M/U COMP ELECTRIC LUBE OIL PUMP RUN STATUS | Being Checked | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XS-210231 | FALSE | 210231 | TRUE | FALSE | FROM BENTLY NEVADA TRIP | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
XS-210233 | FALSE | 210233 | TRUE | FALSE | 2ND STAGE COMPRESSOR FROM BENTLY NEVADA TRIP | Being Checked | 2016-01-08 |  | JACOBS | [7 empty] | FALSE
XS-210239 | FALSE | 210239 | TRUE | FALSE | LUBE OIL PUMP RUN STATUS | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XV-210008 | FALSE | 210008 | TRUE | FALSE | M/U COMP AMPLIFLOW SOLENOID CYCLE CONTROL | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XV-210009 | FALSE | 210009 | TRUE | FALSE | M/U COMP AMPLIFLOW SOLENOID CYCLE CONTROL | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XV-210010 | FALSE | 210010 | TRUE | FALSE | M/U COMP AMPLIFLOW SOLENOID CYCLE CONTROL | Complete - Ready for Startup | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XV-210047 | FALSE | 210047 | TRUE | FALSE | 1ST STAGE RECYCLE AMPLIFLOW SOLENOID CYCLE CONTROL | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XV-210065 | FALSE | 210065 | TRUE | FALSE | 2ND STAGE RECYCLE AMPLIFLOW SOLENOID CYCLE CONTROL | Complete - Ready for Startup | 2016-01-12 |  | JACOBS | [7 empty] | FALSE
XV-210241 | FALSE | 210241 | TRUE | FALSE | LUBE OIL SHUTOFF VALVE SOV | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XV-210243 | FALSE | 210243 | TRUE | FALSE | M/U COMP LUBE OIL SHUTOFF VALVE SOV | Loop Check Failed | 2015-12-04 |  | JACOBS |  |  |  | LOOP VOIDED BY RANDY BONIFAS |  |  |  | FALSE
XY-20064A | FALSE | 20064A | FALSE | FALSE | 1ST STAGE COMPRESSOR PLC START | Being Checked | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XY-20064B | FALSE | 20064B | FALSE | FALSE | 1ST STAGE COMPRESSOR PLC STOP | Being Checked | 2016-01-09 |  | JACOBS | [7 empty] | FALSE
XY-20366A1 | FALSE | 20366A1 | FALSE | FALSE | SPARE LUBE OIL PUMP, STEAM TURBINE, PERMISSIVE | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-20366A2 | FALSE | 20366A2 | FALSE | FALSE | SPARE LUBE OIL PUMP, STEAM TURBINE, PERMISSIVE | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-20366B1 | FALSE | 20366B1 | FALSE | FALSE | STEAM SUPPLY TO LUBE OIL PUMP SPARE | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-20366B2 | FALSE | 20366B2 | FALSE | FALSE | STEAM SUPPLY TO LUBE OIL PUMP SPARE | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-20665 | FALSE | 20665 | FALSE | FALSE | STABILIZER BOTTOMS ASCO | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
XY-20668 | FALSE | 20668 | FALSE | FALSE | FSC TO DCS SPLTR S/D | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
XY-210187D | FALSE | 210187D | FALSE | FALSE | ADS STAGE 1 TRICONEX EIV TRIP | Not Ready for Check |  |  | JACOBS | [7 empty] | FALSE
XY-210197 | FALSE | 210197 | FALSE | FALSE | POWER RECOVERY TURBINE INLET EIV ACTUATION | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
XY-210198 | FALSE | 210198 | FALSE | FALSE | POWER RECOVERY TURBINE OUTLET EIV ACTUATION | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
XY-210228A | FALSE | 210228A | FALSE | FALSE | M/U COMP ELECTRIC LUBE OIL PUMP RUN PERMISSIVE | Being Checked | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XY-210228B | FALSE | 210228B | FALSE | FALSE | M/U COMP ELECTRIC LUBE OIL PUMP AUTO START | Being Checked | 2015-12-04 |  | JACOBS | [7 empty] | FALSE
XY-210239A1 | FALSE | 210239A1 | FALSE | FALSE | LUBE OIL PUMP RUN PERMISSIVE | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-210239A2 | FALSE | 210239A2 | FALSE | FALSE | LUBE OIL PUMP RUN PERMISSIVE | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-210239B1 | FALSE | 210239B1 | FALSE | FALSE | LUBE OIL PUMP AUTO START | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-210239B2 | FALSE | 210239B2 | FALSE | FALSE | LUBE OIL PUMP AUTO START | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-210242 | FALSE | 210242 | TRUE | FALSE | LUBE OIL SHUTOFF VALVE SOV | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
XY-210248 | FALSE | 210248 | TRUE | FALSE | PLC TO DCS RECYCLE COMPRESSOR STAGE 1 TRIPPED | Being Checked | 2016-01-14 |  | JACOBS | [7 empty] | FALSE
XY-210249 | FALSE | 210249 | TRUE | FALSE | PLC TO DCS RECYCLE COMPRESSOR STAGE 2 TRIPPED | Being Checked | 2016-01-13 |  | JACOBS | [7 empty] | FALSE
ZT-20433A | FALSE | 20433A | FALSE | FALSE | SPLITTER DRAFT DOOR A | Not Ready for Check |  |  | RDS | [7 empty] | FALSE
ZT-210197 | FALSE | 210197 | FALSE | FALSE | POWER RECOVERY TURBINE INLET EIV POSITION | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE
ZT-210198 | FALSE | 210198 | FALSE | FALSE | POWER RECOVERY TURBINE OUTLET EIV POSITION | Not Ready for Check |  |  | MATRIX | [7 empty] | FALSE

## Jacobs Instruments from Troy
rev | Instrument No. |  |  | Combined Inst Tag |  | old number | loop folder | P&ID |  |  |  | Description | Source
| PIT | 210005 |  | PIT-210005 |  |  |  | 4305 | R | 00200 | SHT 4 | Ist Stage Compressor Suction Pressure | M-U compr seal gas Instrument List 11-12-15 | 210005
| PIT | 210006 |  | PIT-210006 |  |  |  | 4305 | R | 00200 | SHT 4 | 2ND Stage Compressor Suction Pressure | M-U compr seal gas Instrument List 11-12-15 | 210006
| PIT | 210007 |  | PIT-210007 |  |  |  | 4305 | R | 00200 | SHT 5 | 3RD Stage Compressor Suction Pressure | M-U compr seal gas Instrument List 11-12-15 | 210007
| PIT | 210000 |  | PIT-210000 | C | PIT-100A |  | 4305 | R | 00205B | sht 7 | 3rd Stage Discharge Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210000
| PDIT | 210002 |  | PDIT-210002 | C | PDIT-120A |  | 4305 | R | 00205B | sht 7 | Cleanpac F diferential pressure | M-U compr seal gas Instrument List 11-12-15 | 210002
| LIT | 210001 |  | LIT-210001 | C | LIT-120A |  | 4305 | R | 00205B | sht 7 | Cleanpac F Level | M-U compr seal gas Instrument List 11-12-15 | 210001
| RO | 120 | A | RO-120A |  |  |  | 4305 | R | 00205B | sht 7 | Cleanpac F to 3rd Stage Suction | M-U compr seal gas Instrument List 11-12-15 | 120
| RO | 121 | A | RO-121A |  |  |  | 4305 | R | 00205B | sht 7 | Cleanpac F to 3rd Stage Suction | M-U compr seal gas Instrument List 11-12-15 | 121
| TE | 210003 | A | TE-210003A |  | TE-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | M-U compr seal gas Instrument List 11-12-15 | 210003
| TT | 210003 | A | TT-210003A |  | TE-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | M-U compr seal gas Instrument List 11-12-15 | 210003
2015-07-27 | TC | 210003 |  | TC-210003 |  | TE-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | M-U compr seal gas Instrument List 11-12-15 | 210003
| TE | 210003 | B | TE-210003B |  | TE-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | M-U compr seal gas Instrument List 11-12-15 | 210003
| TSHH | 210003 | A | TSHH-210003A |  | TE-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | M-U compr seal gas Instrument List 11-12-15 | 210003
| TSHH | 210003 | B | TSHH-210003B |  | TE-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | M-U compr seal gas Instrument List 11-12-15 | 210003
| TI | 210003 |  | TI-210003 |  | TI-100A |  | 4305 | R | 00205B | sht 7 |  | M-U compr seal gas Instrument List 11-12-15 | 210003
| PIT | 210011 |  | PIT-210011 | C | PIT-400A |  | 4305 | R | 00205B | sht 8 | Ampliflow IST STAGE Leakage Line Pressure | M-U compr seal gas Instrument List 11-12-15 | 210011
| PCV | 400 | A | PCV-400A |  |  |  | 4305 | R | 00205B | sht 8 | Air supply to Ampliflow | M-U compr seal gas Instrument List 11-12-15 | 400
| PI | 400 | A | PI-400A |  |  |  | 4305 | R | 00205B | sht 8 | Air supply to Ampliflow | M-U compr seal gas Instrument List 11-12-15 | 400
| PIT | 210012 |  | PIT-210012 | C | PIT-401A |  | 4305 | R | 00205B | sht 8 | Ampliflow 2ND STAGE Leakage Line Pressure | M-U compr seal gas Instrument List 11-12-15 | 210012
| PIT | 210013 |  | PIT-210013 | C | PIT-402A |  | 4305 | R | 00205B | sht 8 | Ampliflow 3RD STAGE Leakage Line Pressure | M-U compr seal gas Instrument List 11-12-15 | 210013
| XI | 210008 |  | XI-210008 | C | XE-400 |  |  | R | 00205B | sht 8 | 1st Stage Ampliflow Feedback Sensor | M-U compr seal gas Instrument List 11-12-15 | 210008
| HS | 210008 |  | HS-210008 |  |  |  |  | R | 00205B | sht 8 | 1st Stage Ampliflow Enable | M-U compr seal gas Instrument List 11-12-15 | 210008
| XI | 210009 |  | XI-210009 | C | XE-401 |  |  | R | 00205B | sht 8 | 2nd Stage Ampliflow Feedback Sensor | M-U compr seal gas Instrument List 11-12-15 | 210009
| HS | 210009 |  | HS-210009 | [7 empty] | 2nd Stage Ampliflow Enable | M-U compr seal gas Instrument List 11-12-15 | 210009
| XI | 210010 |  | XI-210010 | C | XE-402 |  |  | R | 00205B | sht 8 | 3rd Stage Ampliflow Feedback Sensor | M-U compr seal gas Instrument List 11-12-15 | 210010
| HS | 210010 |  | HS-210010 |  |  |  |  | R | 00205B | sht 8 | 3rd Stage Ampliflow Enable | M-U compr seal gas Instrument List 11-12-15 | 210010
| PDIT | 210004 |  | PDIT-210004 | C | PDIT-100A |  | 4305 | R | 00205B | sht 7 | Seal Gas Supply Filter Differential Pressure | M-U compr seal gas Instrument List 11-12-15 | 210004
| PDIT | 210014 |  | PDIT-210014 | C | PDIT-200A |  | 4305 | R | 00205B | sht 9 | Separation / Secondary seal gas filter differential pressure | M-U compr seal gas Instrument List 11-12-15 | 210014
| PI | 900 | A | PI-900A |  | PI-900A |  | 4305 | R | 00205B | sht 9 | Gas from 1st Stage, 2nd Stage and 3rd Stage skids to flare | M-U compr seal gas Instrument List 11-12-15 | 900
| PIT | 210016 |  | PIT-210016 | L | PIT-101B |  | 4305 | R | 00200 | SHT 10 | 1st Stage Primary Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210016
| PIT | 210025 |  | PIT-210025 | M | PIT-101C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Primary Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210025
| PIT | 210034 |  | PIT-210034 | H | PIT-101D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Primary Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210034
| FIT | 210015 | A | FIT-210015A | L DCS | FIT-101B |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210015
| FE | 210015 | A | FE-210015A |  | FE-101B |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210015
| FIT | 210024 | A | FIT-210024A | M DCS | FIT-101C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210024
| FE | 210024 | A | FE-210024A |  | FE-101C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210024
| FIT | 210033 | A | FIT-210033A | H DCS | FIT-101D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210033
| FE | 210033 | A | FE-210033A |  | FE-101D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210033
| FIT | 210015 | B | FIT-210015B | L DCS | FIT-102B |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210015
| FE | 210015 | B | FE-210015B |  | FE-102B |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210015
| TI | 101 | B | TI-101B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Gas Temp | M-U compr seal gas Instrument List 11-12-15 | 101
| FIT | 210024 | B | FIT-210024B | M DCS | FIT-102C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210024
| FE | 210024 | B | FE-210024B |  | FE-102C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210024
| TI | 101 | C | TI-101C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Gas Temp | M-U compr seal gas Instrument List 11-12-15 | 101
| FIT | 210033 | B | FIT-210033B | H DCS | FIT-102D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210033
| FE | 210033 | B | FE-210033B |  | FE-102D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210033
| TI | 101 | D | TI-101D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Gas Temp | M-U compr seal gas Instrument List 11-12-15 | 101
| PIT | 210019 |  | PIT-210019 | L | PIT-200B |  | 4305 | R | 00200 | SHT 10 | 1st Stage Separation Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210019
| PCV | 200 | B | PCV-200B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage Separation Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 200
| RO | 201 | B | RO-201B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Separation gas supply | M-U compr seal gas Instrument List 11-12-15 | 201
| RO | 202 | B | RO-202B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Separation gas supply | M-U compr seal gas Instrument List 11-12-15 | 202
| PIT | 210028 |  | PIT-210028 | M | PIT-200C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Separation Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210028
| PCV | 200 | C | PCV-200C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Separation Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 200
| RO | 201 | C | RO-201C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Separation gas supply | M-U compr seal gas Instrument List 11-12-15 | 201
| RO | 202 | C | RO-202C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Separation gas supply | M-U compr seal gas Instrument List 11-12-15 | 202
| PIT | 210037 |  | PIT-210037 | H | PIT-200D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Separation Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 210037
| PCV | 200 | D | PCV-200D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Separation Seal Gas Pressure | M-U compr seal gas Instrument List 11-12-15 | 200
| RO | 201 | D | RO-201D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Separation gas supply | M-U compr seal gas Instrument List 11-12-15 | 201
| RO | 202 | D | RO-202D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Separation gas supply | M-U compr seal gas Instrument List 11-12-15 | 202
| FIT | 210017 |  | FIT-210017 | L | FIT-301B |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Secondary Seal Gas Supply Flow | M-U compr seal gas Instrument List 11-12-15 | 210017
| FE | 210017 |  | FE-210017 |  | FE-301B |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Secondary Seal Gas Supply Flow | M-U compr seal gas Instrument List 11-12-15 | 210017
| PCV | 300 | B | PCV-300B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| PI | 300 | B | PI-300B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| RO | 300 | B | RO-300B |  |  |  | 4305 | R | 00200 | SHT 10 | 1st Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| FIT | 210026 |  | FIT-210026 | M | FIT-301C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210026
| FE | 210026 |  | FE-210026 |  | FE-301C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210026
| PCV | 300 | C | PCV-300C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| PI | 300 | C | PI-300C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| RO | 300 | C | RO-300C |  |  |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| FIT | 210035 |  | FIT-210035 | H | FIT-301D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210035
| FE | 210035 |  | FE-210035 |  | FE-301D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210035
| PCV | 300 | D | PCV-300D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| PI | 300 | D | PI-300D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| RO | 300 | D | RO-300D |  |  |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Seal gas supply | M-U compr seal gas Instrument List 11-12-15 | 300
| FIT | 210018 |  | FIT-210018 | L | FIT-302B |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Secondary Seal Gas Supply Flow | M-U compr seal gas Instrument List 11-12-15 | 210018
| FE | 210018 |  | FE-210018 |  | FE-302B |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Secondary Seal Gas Supply Flow | M-U compr seal gas Instrument List 11-12-15 | 210018
| FIT | 210027 |  | FIT-210027 | M | FIT-302C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210027
| FE | 210027 |  | FE-210027 |  | FE-302C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210027
| FIT | 210036 |  | FIT-210036 | H | FIT-302D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210036
| FE | 210036 |  | FE-210036 |  | FE-302D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Secondary Seal Gas Flow | M-U compr seal gas Instrument List 11-12-15 | 210036
2015-07-27 | PIT | 210021 |  | PIT-210021 | L | PIT-501B |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Leakage Pressure | M-U compr seal gas Instrument List 11-12-15 | 210021
2015-07-27 | PIT | 210030 |  | PIT-210030 | M | PIT-501C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Leakage Pressure | M-U compr seal gas Instrument List 11-12-15 | 210030
2015-07-27 | PIT | 210039 |  | PIT-210039 | H | PIT-501D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Leakage Pressure | M-U compr seal gas Instrument List 11-12-15 | 210039
| FIT | 210023 | A | FIT-210023A | L TRICONEX | FIT-501AB |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210023
| FE | 210023 |  | FE-210023 |  | FE-501AB |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210023
| FIT | 210023 | B | FIT-210023B | L TRICONEX | FIT-501BB |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210023
| FIT | 210023 | C | FIT-210023C | L TRICONEX | FIT-501CB |  | 4305 | R | 00200 | SHT 10 | 1st Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210023
| FIT | 210032 | A | FIT-210032A | M TRICONEX | FIT-501AC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210032
| FE | 210032 |  | FE-210032 |  | FE-501AC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210032
| FIT | 210032 | B | FIT-210032B | M TRICONEX | FIT-501BC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210032
| FIT | 210032 | C | FIT-210032C | M TRICONEX | FIT-501CC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210032
| FIT | 210041 | A | FIT-210041A | H TRICONEX | FIT-501AD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210041
| FE | 210041 |  | FE-210041 |  | FE-501AD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210041
| FIT | 210041 | B | FIT-210041B | H TRICONEX | FIT-501BD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210041
| FIT | 210041 | C | FIT-210041C | H TRICONEX | FIT-501CD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage NDE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210041
2015-07-27 | PIT | 210020 |  | PIT-210020 | L | PIT-502B |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Leakage Pressure | M-U compr seal gas Instrument List 11-12-15 | 210020
2015-07-27 | PIT | 210029 |  | PIT-210029 | M | PIT-502C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Leakage Pressure | M-U compr seal gas Instrument List 11-12-15 | 210029
2015-07-27 | PIT | 210038 |  | PIT-210038 | H | PIT-502D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Leakage Pressure | M-U compr seal gas Instrument List 11-12-15 | 210038
| FIT | 210022 | A | FIT-210022A | L TRICONEX | FIT-502AB |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210022
| FE | 210022 |  | FE-210022 |  | FE-502AB |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210022
| FIT | 210022 | B | FIT-210022B | L TRICONEX | FIT-502BB |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210022
| FIT | 210022 | C | FIT-210022C | L TRICONEX | FIT-502CB |  | 4305 | R | 00200 | SHT 10 | 1st Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210022
| FIT | 210031 | A | FIT-210031A | M TRICONEX | FIT-502AC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210031
| FE | 210031 |  | FE-210031 |  | FE-502AC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210031
| FIT | 210031 | B | FIT-210031B | M TRICONEX | FIT-502BC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210031
| FIT | 210031 | C | FIT-210031C | M TRICONEX | FIT-502CC |  | 4305 | R | 00200 | SHT 11 | 2nd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210031
| FIT | 210040 | A | FIT-210040A | H TRICONEX | FIT-502AD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210040
| FE | 210040 |  | FE-210040 |  | FE-502AD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210040
| FIT | 210040 | B | FIT-210040B | H TRICONEX | FIT-502BD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210040
| FIT | 210040 | C | FIT-210040C | H TRICONEX | FIT-502CD |  | 4305 | R | 00200 | SHT 12 | 3rd Stage DE Primary Seal Leakage Flow | M-U compr seal gas Instrument List 11-12-15 | 210040
| FV | 210015 |  | FV-210015 | L DCS | FCV-100B |  | 4305 | R | 00200 | SHT 10 | 1st Stage Primary Seal Gas Control Valve | M-U compr seal gas Instrument List 11-12-15 | 210015
| PCV | 100 | B | PCV-100B |  |  |  | 4305 | R | 00200 | SHT 10 | N2 supply to FV-210015 | M-U compr seal gas Instrument List 11-12-15 | 100
| FV | 210024 |  | FV-210024 | M DCS | FCV-100C |  | 4305 | R | 00200 | SHT 11 | 2nd Stage Primary Seal Gas Control Valve | M-U compr seal gas Instrument List 11-12-15 | 210024
| PCV | 100 | C | PCV-100C |  |  |  | 4305 | R | 00200 | SHT 11 | N2 supply to FV-210024 | M-U compr seal gas Instrument List 11-12-15 | 100
| FV | 210033 |  | FV-210033 | H DCS | FCV-100D |  | 4305 | R | 00200 | SHT 12 | 3rd Stage Primary Seal Gas Control Valve | M-U compr seal gas Instrument List 11-12-15 | 210033
| PCV | 100 | D | PCV-100D |  |  |  | 4305 | R | 00200 | SHT 12 | N2 supply to FV-210033 | M-U compr seal gas Instrument List 11-12-15 | 100
2 | XA | 210110 |  | XA-210110 |  | CALM-1 | [5 empty] | PLC Card and Instrument Failure Common Alarm, SCADA POINT | M-U compr seal gas Instrument List 11-12-15 | 210110
2 | CALM |  |  | CALM- |  | CALM-2 | [5 empty] | DGS Process Trouble Common Alarm, DELETED POINT | M-U compr seal gas Instrument List 11-12-15
2 | ESD | XS210111 |  | ESD-XS210111 |  | ESD-100 | [5 empty] | ESD trip Signal From Seal View, DELETED POINT | M-U compr seal gas Instrument List 11-12-15 | XS210111
| XL | 210003 | B | XL-210003B |  | HE-131A | [5 empty] | Heater Mode Operation Select | M-U compr seal gas Instrument List 11-12-15 | 210003
| XL | 210003 | A | XL-210003A |  | HE-132a | [5 empty] | Heater On/Off | M-U compr seal gas Instrument List 11-12-15 | 210003
| XY | 210008 |  | XY-210008 | C | XV-400A |  | 4305 | R | 00205B | sht 8 | Ampliflow Solenoid Cycle Control | M-U compr seal gas Instrument List 11-12-15 | 210008
| XY | 210009 |  | XY-210009 | C | XV-401A |  | 4305 | R | 00205B | sht 8 | Ampliflow Solenoid Cycle Control | M-U compr seal gas Instrument List 11-12-15 | 210009
| XY | 210010 |  | XY-210010 | C | XV-402A |  | 4305 | R | 00205B | sht 8 | Ampliflow Solenoid Cycle Control | M-U compr seal gas Instrument List 11-12-15 | 210010
2015-10-12 | XS | 210112 |  | XS-210112 | Was a Scada point only, now changed to hard I/O | ST-100 | [5 empty] | Lube Oil Start Permissive Signal from Seal View | M-U compr seal gas Instrument List 11-12-15 | 210112
3 | TAL | 210003 |  | TAL-210003 |  | ST-101 | [5 empty] | Temperature Start Permissive Signal from Seal View | M-U compr seal gas Instrument List 11-12-15 | 210003
| HS | 219006 |  | HS-219006 |  | Reset | [6 empty] | M-U compr seal gas Instrument List 11-12-15 | 219006
2 | Reset |  |  | Reset- |  | Reset | [5 empty] | DELETED POINT | M-U compr seal gas Instrument List 11-12-15
2 | Enable |  |  | Enable- |  | Enable | [5 empty] | DELETED POINT | M-U compr seal gas Instrument List 11-12-15
| XA | 210003 |  | XA-210003 |  | H-130A | [5 empty] | Heater common alarm | M-U compr seal gas Instrument List 11-12-15 | 210003
2015-09-22 | XA | 20908 |  | XA-20908 | deleted point | [6 empty] | TRICONEX SHUTDOWN SIGNAL TO SEAL GAS PLC | M-U compr seal gas Instrument List 11-12-15 | 20908
2015-09-01 | XS | 210111 |  | XS-210111 | changed Triconex I/O point from BP5-9 to BP5-13 | [6 empty] | Compressor run status from Triconex to PLC | M-U compr seal gas Instrument List 11-12-15 | 210111
1 | PDIT | 20343 |  | PDIT-20343 |  | exist device moved from old panel to seal gas plc | [5 empty] | Lube oil filter differential filter | M-U compr seal gas Instrument List 11-12-15 | 20343
1 | PIT | 20338 |  | PIT-20338 |  | exist device moved from old panel to seal gas plc | [5 empty] | Turbine gland pressure | M-U compr seal gas Instrument List 11-12-15 | 20338
1 | PIT | 20339 |  | PIT-20339 |  | exist device moved from old panel to seal gas plc | [5 empty] | H2 make up turbine steam chest pressure | M-U compr seal gas Instrument List 11-12-15 | 20339
1 | PIT | 20345 |  | PIT-20345 |  | exist device moved from old panel to seal gas plc | [5 empty] | Make up compressor turbine discharge | M-U compr seal gas Instrument List 11-12-15 | 20345
1 | PIT | 20348 |  | PIT-20348 |  | exist device moved from old panel to seal gas plc | [5 empty] | Turbine pilot valve lube oil pressure | M-U compr seal gas Instrument List 11-12-15 | 20348
2015-09-22 | PIT | 20342 |  | PIT-20342 |  | exist device moved from old panel to seal gas plc, changed tag number from 20407 |  | 4305 | R | 00205A | sht 3 | H2 make up turbine steam supply pressure | M-U compr seal gas Instrument List 11-12-15 | 20342
2015-09-22 | TSH | 20341 |  | TSH-20341 |  | exist device moved from old panel to seal gas plc, changed tag number from 20027 |  | 4305 | R | 00205A | sht 5 | standyby lube oil cooler disch temp | M-U compr seal gas Instrument List 11-12-15 | 20341
1 | PSH | 20344 |  | PSH-20344 |  | exist device moved from old panel to seal gas plc |  | 4305 | R | 00205A | sht 3 | turbine seal high leakage | M-U compr seal gas Instrument List 11-12-15 | 20344
2015-10-12 | PB | HOME |  | PB -HOME | deleted point, re-used point for HS-210246 | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | HOME
2015-10-12 | PB | FORWARD |  | PB -FORWARD | deleted point | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | FORWARD
2015-10-12 | PB | BACK |  | PB -BACK | deleted point | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | BACK
2015-07-27 | HS | 210237 |  | HS-210237 | [7 empty] | DGS panel Maintenance mode permissive | M-U compr seal gas Instrument List 11-12-15 | 210237
2015-07-27 | XL | 210237 |  | XL-210237 | [7 empty] | DGS panel Maintenance mode enabled | M-U compr seal gas Instrument List 11-12-15 | 210237
2015-09-22 | XY | 210243 |  | XY-210243 | added Triconex point, changed tag number from 210228 | [6 empty] | LUBE OIL SHUTOFF VALVE SOV | M-U compr seal gas Instrument List 11-12-15 | 210243
2015-09-22 | ZSC | 210243 |  | ZSC-210243 | added Triconex point, changed tag number from 210228 | [6 empty] | LUBE OIL SHUTOFF VALVE CLOSED POSITION | M-U compr seal gas Instrument List 11-12-15 | 210243
2015-09-22 | ZSO | 210243 |  | ZSO-210243 | added Triconex point, changed tag number from 210228 | [6 empty] | LUBE OIL SHUTOFF VALVE OPEN POSITION | M-U compr seal gas Instrument List 11-12-15 | 210243
2015-09-22 | HS | 210228 |  | HS-210228 | added Triconex point on 9/1, deleted Triconex point 9/16' removed the suffix A | [6 empty] | LUBE OIL PUMP HOA IN AUTO | M-U compr seal gas Instrument List 11-12-15 | 210228
2015-09-22 | HS | 20340 |  | HS-20340 | added Triconex point on 9/1, deleted Triconex point 9/16, changed the tag number from 210228B | [6 empty] | SPARE LUBE OIL PUMP, STEAM TURBINE, IN AUTO | M-U compr seal gas Instrument List 11-12-15 | 20340
2015-09-22 | XS | 210228 |  | XS-210228 | added Triconex point, removed the suffix A | [6 empty] | Electric LUBE OIL PUMP RUN STATUS | M-U compr seal gas Instrument List 11-12-15 | 210228
2015-09-22 | XY | 210228 | A | XY-210228A | added Triconex point, change the suffix from B to A | [6 empty] | Electric LUBE OIL PUMP RUN PERMISSIVE | M-U compr seal gas Instrument List 11-12-15 | 210228
2015-09-22 | XY | 210228 | B | XY-210228B | added Triconex point, this point was used for LY-20542 as part of the oil system, changed the suffix from C to B | [6 empty] | Electric LUBE OIL PUMP auto start | M-U compr seal gas Instrument List 11-12-15 | 210228
2015-09-16 | PY | 20340 |  | PY-20340 | Existing Triconex point, need to rework logic | [6 empty] | Output to steam valve for turbine, auto start | M-U compr seal gas Instrument List 11-12-15 | 20340
2015-09-16 | PY | 20340 | A | PY-20340A | added Triconex point | [6 empty] | SPARE LUBE OIL PUMP, STEAM TURBINE, permissive | M-U compr seal gas Instrument List 11-12-15 | 20340
2015-09-16 | PSH | 20340 |  | PSH-20340 | added Triconex point | [6 empty] | SPARE LUBE OIL PUMP, STEAM TURBINE, DISCH PRESSURE | M-U compr seal gas Instrument List 11-12-15 | 20340
2015-09-16 | HS | 20340 |  | HS-20340 | deleted existing Triconex point. Need to rework logic | [6 empty] | Existing Hand switch on panel for Hand / auto for lube oil steam turbine | M-U compr seal gas Instrument List 11-12-15 | 20340
2015-09-16 | LSLL | 20534 |  | LSLL-20534 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20534
2015-09-22 | LSLL | 20535 |  | LSLL-20535 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM, had wrong tag number as 20538, should be 20535 | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20535
2015-09-16 | LSLL | 20536 |  | LSLL-20536 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20536
2015-09-16 | LY | 20542 |  | LY-20542 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20542
2015-09-16 | LSLL | 20542 |  | LSLL-20542 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20542
2015-09-16 | LSLL | 20541 |  | LSLL-20541 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20541
2015-09-16 | LSLL | 20540 |  | LSLL-20540 | deleted existing Triconex point WAS PART OF OIL SEAL SYSTEM | [7 empty] | M-U compr seal gas Instrument List 11-12-15 | 20540
2015-10-12 | HS | 210246 |  | HS-210246 | added point | [6 empty] | ack button | M-U compr seal gas Instrument List 11-12-15 | 210246
2015-10-12 | strobe | 210247 |  | strobe-210247 | added point | [6 empty] | panel strobe | M-U compr seal gas Instrument List 11-12-15 | 210247
| PIT | 210046 |  | PIT-210046 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | Ist Stage Recycle Compressor Suction Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210046
| PIT | 210042 |  | PIT-210042 |  | PIT-100 | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Recycle Compressor Discharge Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210042
| PDIT | 210044 |  | PDIT-210044 |  | PDIT-120 | K2002 | 4305 | R | 00206B | sht 7 | Cleanpac F differential pressure | Recycle compr seal gas Instrument List 7-9-15 | 210044
| LIT | 210043 |  | LIT-210043 |  | LIT-120 | K2002 | 4305 | R | 00206B | sht 7 | Cleanpac F Level | Recycle compr seal gas Instrument List 7-9-15 | 210043
| RO | 120 |  | RO-120 |  |  | K2002 | 4305 | R | 00205B | sht 7 | Cleanpac F to 1st stage recycle Suction | Recycle compr seal gas Instrument List 7-9-15 | 120
| RO | 121 |  | RO-121 |  |  | K2002 | 4305 | R | 00205B | sht 7 | Cleanpac F to 1st stage recycle Suction | Recycle compr seal gas Instrument List 7-9-15 | 121
| TE | 210045 | A | TE-210045A |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210045
| TC | 210045 |  | TC-210045 |  | TE-100 | K2002 | 4305 | R | 00206B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210045
| TE | 210045 | B | TE-210045B |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210045
| TSHH | 210045 | A | TSHH-210045A |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210045
| TSHH | 210045 | B | TSHH-210045B |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210045
| TI | 210045 |  | TI-210045 |  | TI-100 | K2002 | 4305 | R | 00205B | sht 7 |  | Recycle compr seal gas Instrument List 7-9-15 | 210045
| XV | 210047 |  | XV-210047 |  |  | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Recycle Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 7-9-15 | 210047
| XI | 210047 |  | XI-210047 |  |  | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Recycle Ampliflow Solenoid Cycle Feedback | Recycle compr seal gas Instrument List 7-9-15 | 210047
| PCV | 400 |  | PCV-400 |  | PCV-400 | K2002 | 4305 | R | 00205B | sht 7 | 1st Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 7-9-15 | 400
| PI | 400 |  | PI-400 |  | PI-400 | K2002 | 4305 | R | 00205B | sht 7 | 1st Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 7-9-15 | 400
| PDIT | 210050 |  | PDIT-210050 |  | PDIT-200 | K2002 | 4305 | R | 00206B | sht 8 | Nitrogen Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 7-9-15 | 210050
| PDIT | 210049 |  | PDIT-210049 |  | PDIT-100 | K2002 | 4305 | R | 00206B | sht 8 | Seal Gas Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 7-9-15 | 210049
| PIT | 210048 |  | PIT-210048 |  | PIT-300 | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Ampliflow process leakage to flare | Recycle compr seal gas Instrument List 7-9-15 | 210048
| PIT | 210052 |  | PIT-210052 |  | PIT-101 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor Primary Seal Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210052
| FIT | 210051 | A | FIT-210051A | L DCS | FIT-101 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210051
| FE | 210051 | A | FE-210051A |  | FE-101 | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210051
| FIT | 210051 | B | FIT-210051B | L DCS | FIT-102 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210051
| FE | 210051 | B | FE-210051B |  | FE-102B | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210051
| TI | 101 |  | TI-101 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Gas Temp | Recycle compr seal gas Instrument List 7-9-15 | 101
| PIT | 210055 |  | PIT-210055 |  | PIT-200 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210055
| PCV | 200 |  | PCV-200 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 200
| RO | 201 |  | RO-201 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Separation gas supply | Recycle compr seal gas Instrument List 7-9-15 | 201
| RO | 202 |  | RO-202 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DNE Separation gas supply | Recycle compr seal gas Instrument List 7-9-15 | 202
| FIT | 210053 |  | FIT-210053 |  | FIT-301 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210053
| FE | 210053 |  | FE-210053 |  | FE-301 | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210053
| PCV | 300 |  | PCV-300 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 7-9-15 | 300
| PI | 300 |  | PI-300 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 7-9-15 | 300
| RO | 300 |  | RO-300 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 7-9-15 | 300
| FIT | 210054 |  | FIT-210054 |  | FIT-302 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210054
| FE | 210054 |  | FE-210054 |  | FE-302 | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210054
| PIT | 210057 |  | PIT-210057 |  | PIT-501 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210057
| FIT | 210059 | A | FIT-210059A |  | FIT-501A | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210059
| FE | 210059 |  | FE-210059 |  | FE-501AB | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210059
| FIT | 210059 | B | FIT-210059B |  | FIT-501B | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210059
| FIT | 210059 | C | FIT-210059C |  | FIT-501C | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210059
| PIT | 210056 |  | PIT-210056 |  | PIT-502 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210056
| FIT | 210058 | A | FIT-210058A |  | FIT-502A | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210058
| FE | 210058 |  | FE-210058 |  | FE-502AB | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210058
| FIT | 210058 | B | FIT-210058B |  | FIT-502B | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210058
| FIT | 210058 | C | FIT-210058C |  | FIT-502C | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210058
| FV | 210051 |  | FV-210051 | L DCS | FCV-100 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor Primary Seal Gas Control Valve | Recycle compr seal gas Instrument List 7-9-15 | 210051
| PCV | 100 |  | PCV-100 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | N2 supply to FV-210051 | Recycle compr seal gas Instrument List 7-9-15 | 100
| CALM |  |  | CALM- |  | CALM-1 | K2002 |  |  |  |  | PLC Card and Instrument Failure Common Alarm | Recycle compr seal gas Instrument List 7-9-15
| CALM |  |  | CALM- |  | CALM-2 | K2002 |  |  |  |  | DGS Process Trouble Common Alarm | Recycle compr seal gas Instrument List 7-9-15
| ESD |  |  | ESD- |  | ESD-100 | K2002 |  |  |  |  | ESD trip Signal From Seal View | Recycle compr seal gas Instrument List 7-9-15
| XL | 210045 | B | XL-210045B |  | HE-131 | K2002 | 4305 | R | 00206B | SHT 7 | Heater Mode Operation Select | Recycle compr seal gas Instrument List 7-9-15 | 210045
| XL | 210045 | A | XL-210045A |  | HE-132 | K2002 | 4305 | R | 00206B | SHT 7 | Heater On/Off | Recycle compr seal gas Instrument List 7-9-15 | 210045
| ST |  |  | ST- |  | ST-100 | K2002 |  |  |  |  | Lube Oil Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 7-9-15
| ST |  |  | ST- |  | ST-101 | K2002 |  |  |  |  | Temperature Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 7-9-15
| Reset |  |  | Reset- |  | Reset | K2002 | [5 empty] | Recycle compr seal gas Instrument List 7-9-15
| Reset |  |  | Reset- |  | Reset | K2002 | [5 empty] | Recycle compr seal gas Instrument List 7-9-15
| Enable |  |  | Enable- |  | Enable | K2002 | [5 empty] | Recycle compr seal gas Instrument List 7-9-15
| XA | 210045 |  | XA-210045 |  | H-130 | K2002 | 4305 | R | 00206B | SHT 7 | Heater common alarm | Recycle compr seal gas Instrument List 7-9-15 | 210045
| HS | HOME |  | HS-HOME |  |  | K2002 |  |  |  |  | HMI HOME BUTTON | Recycle compr seal gas Instrument List 7-9-15 | HOME
| HS | FORWARD |  | HS-FORWARD |  |  | K2002 |  |  |  |  | HMI FORWARD BUTTON | Recycle compr seal gas Instrument List 7-9-15 | FORWARD
| HS | BACK |  | HS-BACK |  |  | K2002 |  |  |  |  | HMI BACK BUTTON | Recycle compr seal gas Instrument List 7-9-15 | BACK
| HS | 210223 |  | HS-210223 |  |  | K2002 |  |  |  |  | reset button | Recycle compr seal gas Instrument List 7-9-15 | 210223
| HS | 210222 |  | HS-210222 |  |  | K2002 |  |  |  |  | ack button | Recycle compr seal gas Instrument List 7-9-15 | 210222
| HS | 210224 |  | HS-210224 |  |  | K2002 |  |  |  |  | test aux lube pump button | Recycle compr seal gas Instrument List 7-9-15 | 210224
| HS | 210225 |  | HS-210225 |  |  | K2002 |  |  |  |  | maintenance mode ss | Recycle compr seal gas Instrument List 7-9-15 | 210225
| XL | 210225 |  | XL-210225 |  |  | K2002 |  |  |  |  | maintenance mode light | Recycle compr seal gas Instrument List 7-9-15 | 210225
| FI | 20101 |  | FI-20101 |  |  | K2002 | 4305 | R | 00201 | SHT 3 | 1st stage recycle compressor disch flow, purchse new indicator and mount on column near the old panel | Recycle compr seal gas Instrument List 7-9-15 | 20101
sd | LIT | 20504 |  | LIT-20504 |  |  | K2002 | 4305 | R | 00201 | SHT 6 | 1st stage high pressure separator, change from level switch to a transmitter | Recycle compr seal gas Instrument List 7-9-15 | 20504
| PIT | 20414 |  | PIT-20414 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor disch pressure | Recycle compr seal gas Instrument List 7-9-15 | 20414
| TIT | 20015 |  | TIT-20015 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor disch temperature, retag TE-20T024 and add a TIT, demo TSH-20015 | Recycle compr seal gas Instrument List 7-9-15 | 20015
| TSH | 20015 |  | TSH-20015 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | DEMO AND REPLACE WITH TIT-20015 | Recycle compr seal gas Instrument List 7-9-15 | 20015
| TE | 20T024 |  | TE-20T024 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | RETAG AS TE-20015 | Recycle compr seal gas Instrument List 7-9-15 | 20T024
sd | CTA | 210234 |  | CTA-210234 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | FROM Bently Nevada PANEL PURGE ALARM | Recycle compr seal gas Instrument List 7-9-15 | 210234
sd | CTA | 210230 |  | CTA-210230 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | Bently Nevada common trouble alarm | Recycle compr seal gas Instrument List 7-9-15 | 210230
| XS | 20064 |  | XS-20064 |  |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor run status | Recycle compr seal gas Instrument List 7-9-15 | 20064
sd | XS | 210231 |  | XS-210231 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | FROM BENTLY NEVADA TRIP | Recycle compr seal gas Instrument List 7-9-15 | 210231
sd | HS | 20064 | A | HS-20064A |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mounted start | Recycle compr seal gas Instrument List 7-9-15 | 20064
| XL | 20064 | A | XL-20064A |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mounted start light | Recycle compr seal gas Instrument List 7-9-15 | 20064
| HS | 20064 | AA | HS-20064AA |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor FIELD mounted start | Recycle compr seal gas Instrument List 7-9-15 | 20064
sd | HS | 20064 | B | HS-20064B |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mtd stop | Recycle compr seal gas Instrument List 7-9-15 | 20064
| XL | 20064 | B | XL-20064B |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mtd stop light | Recycle compr seal gas Instrument List 7-9-15 | 20064
| HS | 20064 | BA | HS-20064BA |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor FIELD mtd stop | Recycle compr seal gas Instrument List 7-9-15 | 20064
| HS | 210235 |  | HS-210235 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor E stop | Recycle compr seal gas Instrument List 7-9-15 | 210235
| HV | 20610 |  | HV-20610 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | add DVC to valve | Recycle compr seal gas Instrument List 7-9-15 | 20610
| IE | 20643 |  | IE-20643 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor amps | Recycle compr seal gas Instrument List 7-9-15 | 20643
sd | PIT | 20410 | A | PIT-20410A |  |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor lube oil pressure | Recycle compr seal gas Instrument List 7-9-15 | 20410
sd | PIT | 20410 | B | PIT-20410B |  |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor lube oil pressure | Recycle compr seal gas Instrument List 7-9-15 | 20410
sd | XS | 20064 | A | XS-20064A |  |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor PLC start | Recycle compr seal gas Instrument List 7-9-15 | 20064
sd | XS | 20064 | B | XS-20064B |  |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor PLC stop | Recycle compr seal gas Instrument List 7-9-15 | 20064
sd | PY | 20366 |  | PY-20366 |  |  | K2002 | 4305 | R | 00206A | SHT 3 | Steam supply to lube oil pump spare, need an output from each PLC, REplace 125 VDC sov with 24 vdc sov | Recycle compr seal gas Instrument List 7-9-15 | 20366
sd | PIT | 20366 | A | PIT-20366A |  |  | K2002 | 4305 | R | 00206A | SHT 4 | lube oil pump pressure, change psl to two PIT's | Recycle compr seal gas Instrument List 7-9-15 | 20366
| CTA | 210216 |  | CTA-210216 |  |  | K2002 |  |  |  |  | Recycle 1 PLC power supply alarm | Recycle compr seal gas Instrument List 7-9-15 | 210216
| STROBE | 210218 |  | STROBE-210218 |  |  | K2002 |  |  |  |  | Recycle 1 PLC Beacon | Recycle compr seal gas Instrument List 7-9-15 | 210218
| PSL | 210220 |  | PSL-210220 |  |  | K2002 |  |  |  |  | PLC panel purge alarm | Recycle compr seal gas Instrument List 7-9-15 | 210220
| TIT | 210221 |  | TIT-210221 |  |  | K2002 |  |  |  |  | PLC panel temperature | Recycle compr seal gas Instrument List 7-9-15 | 210221
| PIT | 210064 |  | PIT-210064 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2ND Stage Recycle Compressor Suction Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210064
| PIT | 210060 |  | PIT-210060 |  | PIT-100 | K2003 | 4305 | R | 00206B | sht 10 | 1st Stage Recycle Compressor Discharge Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210060
| PDIT | 210062 |  | PDIT-210062 |  | PDIT-120 | K2003 | 4305 | R | 00206B | sht 10 | Cleanpac F diferential pressure | Recycle compr seal gas Instrument List 7-9-15 | 210062
| LIT | 210061 |  | LIT-210061 |  | LIT-120 | K2003 | 4305 | R | 00206B | sht 10 | Cleanpac F Level | Recycle compr seal gas Instrument List 7-9-15 | 210061
| RO | 120 |  | RO-120 |  |  | K2003 | 4305 | R | 00205B | sht 7 | Cleanpac F to 2nd stage recycle Suction | Recycle compr seal gas Instrument List 7-9-15 | 120
| RO | 121 |  | RO-121 |  |  | K2003 | 4305 | R | 00205B | sht 7 | Cleanpac F to 2nd stage recycle Suction | Recycle compr seal gas Instrument List 7-9-15 | 121
| TE | 210063 | A | TE-210063A |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210063
| TC | 210063 |  | TC-210063 |  | TE-100A | K2003 | 4305 | R | 00205B | sht 10 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210063
| TE | 210063 | B | TE-210063B |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210063
| TSHH | 210063 | A | TSHH-210063A |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210063
| TSHH | 210063 | B | TSHH-210063B |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 7-9-15 | 210063
| TI | 210063 |  | TI-210063 |  | TI-100A | K2003 | 4305 | R | 00205B | sht 7 |  | Recycle compr seal gas Instrument List 7-9-15 | 210063
| XV | 210065 |  | XV-210065 |  |  | K2003 | 4305 | R | 00206B | sht 10 | 2nd Stage Recycle Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 7-9-15 | 210065
| XI | 210065 |  | XI-210065 |  |  | K2003 | 4305 | R | 00206B | sht 10 | 2nd Stage Recycle Ampliflow Solenoid Cycle Feedback | Recycle compr seal gas Instrument List 7-9-15 | 210065
| PCV | 400 |  | PCV-400 |  | PCV-400 | K2003 | 4305 | R | 00205B | sht 7 | 2nd Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 7-9-15 | 400
| PI | 400 |  | PI-400 |  | PI-400 | K2003 | 4305 | R | 00205B | sht 7 | 2nd Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 7-9-15 | 400
| PDIT | 210068 |  | PDIT-210068 |  | PDIT-200 | K2003 | 4305 | R | 00206B | sht 11 | Nitrogen Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 7-9-15 | 210068
| PDIT | 210067 |  | PDIT-210067 |  | PDIT-100 | K2003 | 4305 | R | 00206B | sht 11 | Seal Gas Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 7-9-15 | 210067
| PIT | 210066 |  | PIT-210066 |  | PIT-300 | K2003 | 4305 | R | 00206B | sht 10 | 2nd Stage Ampliflow process leaksge to flare | Recycle compr seal gas Instrument List 7-9-15 | 210066
| PIT | 210070 |  | PIT-210070 |  | PIT-101 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor Primary Seal Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210070
| FIT | 210069 | A | FIT-210069A | L DCS | FIT-101 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210069
| FE | 210069 | A | FE-210069A |  | FE-101 | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210069
| FIT | 210069 | B | FIT-210069B | L DCS | FIT-102 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210069
| FE | 210069 | B | FE-210069B |  | FE-102B | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 7-9-15 | 210069
| TI | 101 |  | TI-101 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Gas Temp | Recycle compr seal gas Instrument List 7-9-15 | 101
| PIT | 210073 |  | PIT-210073 |  | PIT-200 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210073
| PCV | 200 |  | PCV-200 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 7-9-15 | 200
| RO | 201 |  | RO-201 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Separation gas supply | Recycle compr seal gas Instrument List 7-9-15 | 201
| RO | 202 |  | RO-202 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DNE Separation gas supply | Recycle compr seal gas Instrument List 7-9-15 | 202
| FIT | 210071 |  | FIT-210071 |  | FIT-301 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210071
| FE | 210071 |  | FE-210071 |  | FE-301 | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210071
| PCV | 300 |  | PCV-300 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 7-9-15 | 300
| PI | 300 |  | PI-300 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 7-9-15 | 300
| RO | 300 |  | RO-300 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 7-9-15 | 300
| FIT | 210072 |  | FIT-210072 |  | FIT-302 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210072
| FE | 210072 |  | FE-210072 |  | FE-302 | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 7-9-15 | 210072
| PIT | 210075 |  | PIT-210075 |  | PIT-501 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210075
| FIT | 210077 | A | FIT-210077A |  | FIT-501A | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210077
| FE | 210077 |  | FE-210077 |  | FE-501AB | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210077
| FIT | 210077 | B | FIT-210077B |  | FIT-501B | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210077
| FIT | 210077 | C | FIT-210077C |  | FIT-501C | K2003 | 4305 | R | 00206B | SHT 12 | 2ndt Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210077
| PIT | 210074 |  | PIT-210074 |  | PIT-502 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 7-9-15 | 210074
| FIT | 210076 | A | FIT-210076A |  | FIT-502A | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210076
| FE | 210076 |  | FE-210076 |  | FE-502AB | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210076
| FIT | 210076 | B | FIT-210076B |  | FIT-502B | K2003 | 4305 | R | 00206B | SHT 12 | 2ndt Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210076
| FIT | 210076 | C | FIT-210076C |  | FIT-502C | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 7-9-15 | 210076
| FV | 210069 |  | FV-210069 | L DCS | FCV-100 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor Primary Seal Gas Control Valve | Recycle compr seal gas Instrument List 7-9-15 | 210069
| PCV | 100 |  | PCV-100 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | N2 supply to FV-210069 | Recycle compr seal gas Instrument List 7-9-15 | 100
| CALM |  |  | CALM- |  | CALM-1 | K2003 |  |  |  |  | PLC Card and Instrument Failure Common Alarm | Recycle compr seal gas Instrument List 7-9-15
| CALM |  |  | CALM- |  | CALM-2 | K2003 |  |  |  |  | DGS Process Trouble Common Alarm | Recycle compr seal gas Instrument List 7-9-15
| ESD |  |  | ESD- |  | ESD-100 | K2003 |  |  |  |  | ESD trip Signal From Seal View | Recycle compr seal gas Instrument List 7-9-15
| XL | 210063 | B | XL-210063B |  | HE-131 | K2003 | 4305 | R | 00206B | SHT 10 | Heater Mode Operation Select | Recycle compr seal gas Instrument List 7-9-15 | 210063
| XL | 210063 | A | XL-210063A |  | HE-132 | K2003 | 4305 | R | 00206B | SHT 10 | Heater On/Off | Recycle compr seal gas Instrument List 7-9-15 | 210063
| ST |  |  | ST- |  | ST-100 | K2003 |  |  |  |  | Lube Oil Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 7-9-15
| ST |  |  | ST- |  | ST-101 | K2003 |  |  |  |  | Temperature Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 7-9-15
| Reset |  |  | Reset- |  | Reset | K2003 | [5 empty] | Recycle compr seal gas Instrument List 7-9-15
| Reset |  |  | Reset- |  | Reset | K2003 | [5 empty] | Recycle compr seal gas Instrument List 7-9-15
| Enable |  |  | Enable- |  | Enable | K2003 | [5 empty] | Recycle compr seal gas Instrument List 7-9-15
| XA | 210063 |  | XA-210063 |  | H-130 | K2003 | 4305 | R | 00206B | SHT 10 | Heater common alarm | Recycle compr seal gas Instrument List 7-9-15 | 210063
| HS | HOME |  | HS-HOME |  |  | K2003 |  |  |  |  | HMI HOME BUTTON | Recycle compr seal gas Instrument List 7-9-15 | HOME
| HS | FORWARD |  | HS-FORWARD |  |  | K2003 |  |  |  |  | HMI FORWARD BUTTON | Recycle compr seal gas Instrument List 7-9-15 | FORWARD
| HS | BACK |  | HS-BACK |  |  | K2003 |  |  |  |  | HMI BACK BUTTON | Recycle compr seal gas Instrument List 7-9-15 | BACK
| HS | 210227 |  | HS-210227 |  |  | K2003 |  |  |  |  | reset button | Recycle compr seal gas Instrument List 7-9-15 | 210227
| HS | 210226 |  | HS-210226 |  |  | K2003 |  |  |  |  | ack button | Recycle compr seal gas Instrument List 7-9-15 | 210226
| HS | 210028 |  | HS-210028 |  |  | K2003 |  |  |  |  | testAUX PUMP button | Recycle compr seal gas Instrument List 7-9-15 | 210028
| HS | 210229 |  | HS-210229 |  |  | K2003 |  |  |  |  | maintenance mode ss | Recycle compr seal gas Instrument List 7-9-15 | 210229
| XL | 210229 |  | XL-210229 |  |  | K2003 |  |  |  |  | maintenance mode light | Recycle compr seal gas Instrument List 7-9-15 | 210229
| FI | 20108 |  | FI-20108 |  |  | K2003 |  |  |  |  | 2nd stage recycle compressor disch flow, purchse new indicator and mount on column near the old panel | Recycle compr seal gas Instrument List 7-9-15 | 20108
sd | LIT | 20529 |  | LIT-20529 |  |  | K2003 | 4305 | R | 00202 | SHT 6 | 2nd stage high pressure separator, change from level switch to a transmitter | Recycle compr seal gas Instrument List 7-9-15 | 20529
| PIT | 20416 |  | PIT-20416 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor disch pressure | Recycle compr seal gas Instrument List 7-9-15 | 20416
| TIT | 20025 |  | TIT-20025 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor disch temperature, retag TE-20T046 and add a TIT, demo TSH-20025 | Recycle compr seal gas Instrument List 7-9-15 | 20025
| TSH | 20025 |  | TSH-20025 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | DEMO AND REPLACE WITH TIT-20025 | Recycle compr seal gas Instrument List 7-9-15 | 20025
| TE | 20T046 |  | TE-20T046 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | RETAG AS TE-20025 | Recycle compr seal gas Instrument List 7-9-15 | 20T046
sd | XS | 210233 |  | XS-210233 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FROM BENTLY NEVADA TRIP | Recycle compr seal gas Instrument List 7-9-15 | 210233
sd | CTA | 210232 |  | CTA-210232 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | Bently Nevada common trouble alarm | Recycle compr seal gas Instrument List 7-9-15 | 210232
| XS | 20065 |  | XS-20065 |  |  | K2003 | 4305 | R | 00206 | SHT 3 | 2nd stage compressor run status | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | TSH | 20026 |  | TSH-20026 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | FROM BENTLY NEVADA | Recycle compr seal gas Instrument List 7-9-15 | 20026
sd | HS | 20065 | A | HS-20065A |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mounted start | Recycle compr seal gas Instrument List 7-9-15 | 20065
| XL | 20065 | A | XL-20065A |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mounted statr light | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | HS | 20065 | AA | HS-20065AA |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FIELD mounted start | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | HS | 20065 | B | HS-20065B |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mtd stop | Recycle compr seal gas Instrument List 7-9-15 | 20065
| XL | 20065 | B | XL-20065B |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mtd stop light | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | HS | 20065 | BA | HS-20065BA |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FIELD mtd stop | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | HS | 210236 |  | HS-210236 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor E stop | Recycle compr seal gas Instrument List 7-9-15 | 210236
| HV | 20608 |  | HV-20608 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | add DVC to valve | Recycle compr seal gas Instrument List 7-9-15 | 20608
| IE | 20616 |  | IE-20616 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor amps | Recycle compr seal gas Instrument List 7-9-15 | 20616
sd | PIT | 20317 | A | PIT-20317A |  |  | K2003 | 4305 | R | 00206A | SHT 3 | 2nd stage compressor lube oil pressure | Recycle compr seal gas Instrument List 7-9-15 | 20317
sd | PIT | 20317 | B | PIT-20317B |  |  | K2003 | 4305 | R | 00206A | SHT 3 | 2nd stage compressor lube oil pressure | Recycle compr seal gas Instrument List 7-9-15 | 20317
sd | XS | 20065 | A | XS-20065A |  |  | K2003 | 4305 | R | 00206 | SHT 3 | 2nd stage compressor PLC start | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | XS | 20065 | B | XS-20065B |  |  | K2003 | 4305 | R | 00206 | SHT 3 | 2nd stage compressor PLC stop | Recycle compr seal gas Instrument List 7-9-15 | 20065
sd | PY | 20366 | B | PY-20366B |  |  | K2003 | 4305 | R | 00206A | SHT 3 | Steam supply to lube oil pump spare, need an output from each PLC, REplace 125 VDC sov with 24 vdc sov | Recycle compr seal gas Instrument List 7-9-15 | 20366
| PSH | 20355 |  | PSH-20355 |  |  | K2003 | 4305 | R | 00206A | SHT 3 | lube oil spare pump disch pressure, to only one of the PLC's | Recycle compr seal gas Instrument List 7-9-15 | 20355
| PDIT | 20352 |  | PDIT-20352 |  |  | K2003 | 4305 | R | 00206A | SHT 4 | lube oil filter diff pressure, to only one of the PLC's | Recycle compr seal gas Instrument List 7-9-15 | 20352
| TSH | 20028 |  | TSH-20028 |  |  | K2003 | 4305 | R | 00206A | SHT 4 | lube oil filter diff temperature, to only one of the PLC's | Recycle compr seal gas Instrument List 7-9-15 | 20028
sd | PIT | 20366 | B | PIT-20366B |  |  | K2003 | 4305 | R | 00206A | SHT 4 | lube oil pump pressure, change psl to two PIT's | Recycle compr seal gas Instrument List 7-9-15 | 20366
| CTA | 210217 |  | CTA-210217 |  |  | K2003 |  |  |  |  | Recycle 2 PLC power supply alarm | Recycle compr seal gas Instrument List 7-9-15 | 210217
| STROBE | 210219 |  | STROBE-210219 |  |  | K2003 |  |  |  |  | Recycle 2 PLC Beacon | Recycle compr seal gas Instrument List 7-9-15 | 210219
| LIT | 20541 |  | LIT-20541 |  |  | DEMO | 4305 | R | 00206B | SHT 3 | 2ND STAGE SEAL OIL TANK | Recycle compr seal gas Instrument List 7-9-15 | 20541
| LIT | 20542 |  | LIT-20542 |  |  | DEMO | 4305 | R | 00206B | SHT 6 | 1ST STAGE SEAL OIL TANK | Recycle compr seal gas Instrument List 7-9-15 | 20542
| PSH | 20389 |  | PSH-20389 |  |  | DEMO | 4305 | R | 00206B | SHT 4 | 1ST AND 2ND STAGE REC COMP SP SO | Recycle compr seal gas Instrument List 7-9-15 | 20389
| PDIT | 20383 |  | PDIT-20383 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL DIFFERENTIALS | Recycle compr seal gas Instrument List 7-9-15 | 20383
| PIT | 20390 |  | PIT-20390 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL 2ND STAGE | Recycle compr seal gas Instrument List 7-9-15 | 20390
| PIT | 20391 |  | PIT-20391 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL 1ST STAGE | Recycle compr seal gas Instrument List 7-9-15 | 20391
| PDIT | 20385 |  | PDIT-20385 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL FILTER DIFFERENTIAL | Recycle compr seal gas Instrument List 7-9-15 | 20385
| PDIT | 20384 |  | PDIT-20384 |  |  | DEMO | 4305 | R | 00206B | SHT 6 | SEAL OIL 1ST STAGE | Recycle compr seal gas Instrument List 7-9-15 | 20384
| FI | 20101 |  | FI-20101 |  |  | REWIRE | 4305 | R | 00201 | SHT 3 | 1ST STAGE FEED | Recycle compr seal gas Instrument List 7-9-15 | 20101
| FI | 20108 |  | FI-20108 |  |  | REWIRE | 4305 | R | 00202 | SHT 3 | 2ND STAGE FEED | Recycle compr seal gas Instrument List 7-9-15 | 20108
| PIT | 210046 |  | PIT-210046 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | Ist Stage Recycle Compressor Suction Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210046
| PIT | 210042 |  | PIT-210042 | C | PIT-100 | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Recycle Compressor Discharge Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210042
| PDIT | 210044 |  | PDIT-210044 | C | PDIT-120 | K2002 | 4305 | R | 00206B | sht 7 | Cleanpac F differential pressure | Recycle compr seal gas Instrument List 11-12-15 | 210044
| LIT | 210043 |  | LIT-210043 | C | LIT-120 | K2002 | 4305 | R | 00206B | sht 7 | Cleanpac F Level | Recycle compr seal gas Instrument List 11-12-15 | 210043
| RO | 120 |  | RO-120 |  |  | K2002 | 4305 | R | 00205B | sht 7 | Cleanpac F to 1st stage recycle Suction | Recycle compr seal gas Instrument List 11-12-15 | 120
| RO | 121 |  | RO-121 |  |  | K2002 | 4305 | R | 00205B | sht 7 | Cleanpac F to 1st stage recycle Suction | Recycle compr seal gas Instrument List 11-12-15 | 121
| TE | 210045 | A | TE-210045A |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210045
| TC | 210045 |  | TC-210045 |  | TE-100 | K2002 | 4305 | R | 00206B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210045
| TE | 210045 | B | TE-210045B |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210045
| TSHH | 210045 | A | TSHH-210045A |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210045
| TSHH | 210045 | B | TSHH-210045B |  | TE-100 | K2002 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210045
| TI | 210045 |  | TI-210045 |  | TI-100 | K2002 | 4305 | R | 00205B | sht 7 |  | Recycle compr seal gas Instrument List 11-12-15 | 210045
| XV | 210047 |  | XV-210047 |  |  | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Recycle Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 11-12-15 | 210047
| XI | 210047 |  | XI-210047 | C |  | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Recycle Ampliflow Solenoid Cycle Feedback | Recycle compr seal gas Instrument List 11-12-15 | 210047
| PCV | 400 |  | PCV-400 |  | PCV-400 | K2002 | 4305 | R | 00205B | sht 7 | 1st Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 11-12-15 | 400
| PI | 400 |  | PI-400 |  | PI-400 | K2002 | 4305 | R | 00205B | sht 7 | 1st Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 11-12-15 | 400
| PDIT | 210050 |  | PDIT-210050 | C | PDIT-200 | K2002 | 4305 | R | 00206B | sht 8 | Nitrogen Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 11-12-15 | 210050
| PDIT | 210049 |  | PDIT-210049 | C | PDIT-100 | K2002 | 4305 | R | 00206B | sht 8 | Seal Gas Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 11-12-15 | 210049
| PIT | 210048 |  | PIT-210048 | C | PIT-300 | K2002 | 4305 | R | 00206B | sht 7 | 1st Stage Ampliflow process leakage to flare | Recycle compr seal gas Instrument List 11-12-15 | 210048
| PIT | 210052 |  | PIT-210052 | L | PIT-101 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor Primary Seal Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210052
| FIT | 210051 | A | FIT-210051A | L DCS | FIT-101 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210051
| FE | 210051 | A | FE-210051A |  | FE-101 | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210051
| FIT | 210051 | B | FIT-210051B | L DCS | FIT-102 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210051
| FE | 210051 | B | FE-210051B |  | FE-102B | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210051
| TI | 101 |  | TI-101 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Gas Temp | Recycle compr seal gas Instrument List 11-12-15 | 101
| PIT | 210055 |  | PIT-210055 | L | PIT-200 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210055
| PCV | 200 |  | PCV-200 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 200
| RO | 201 |  | RO-201 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Separation gas supply | Recycle compr seal gas Instrument List 11-12-15 | 201
| RO | 202 |  | RO-202 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DNE Separation gas supply | Recycle compr seal gas Instrument List 11-12-15 | 202
| FIT | 210053 |  | FIT-210053 | L | FIT-301 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210053
| FE | 210053 |  | FE-210053 |  | FE-301 | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210053
| PCV | 300 |  | PCV-300 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 11-12-15 | 300
| PI | 300 |  | PI-300 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 11-12-15 | 300
| RO | 300 |  | RO-300 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 11-12-15 | 300
| FIT | 210054 |  | FIT-210054 | L | FIT-302 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210054
| FE | 210054 |  | FE-210054 |  | FE-302 | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210054
| PIT | 210057 |  | PIT-210057 | L | PIT-501 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210057
| FIT | 210059 | A | FIT-210059A |  | FIT-501A | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210059
| FE | 210059 |  | FE-210059 |  | FE-501AB | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210059
| FIT | 210059 | B | FIT-210059B |  | FIT-501B | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210059
| FIT | 210059 | C | FIT-210059C |  | FIT-501C | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210059
| PIT | 210056 |  | PIT-210056 | L | PIT-502 | K2002 | 4305 | R | 00206B | sht 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210056
| FIT | 210058 | A | FIT-210058A |  | FIT-502A | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210058
| FE | 210058 |  | FE-210058 |  | FE-502AB | K2002 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210058
| FIT | 210058 | B | FIT-210058B |  | FIT-502B | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210058
| FIT | 210058 | C | FIT-210058C |  | FIT-502C | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210058
| FV | 210051 |  | FV-210051 | L DCS | FCV-100 | K2002 | 4305 | R | 00206B | SHT 9 | 1st Stage Recycle Compressor Primary Seal Gas Control Valve | Recycle compr seal gas Instrument List 11-12-15 | 210051
| PCV | 100 |  | PCV-100 |  |  | K2002 | 4305 | R | 00200 | SHT 10 | N2 supply to FV-210051 | Recycle compr seal gas Instrument List 11-12-15 | 100
| CALM |  |  | CALM- |  | CALM-1 | K2002 |  |  |  |  | PLC Card and Instrument Failure Common Alarm | Recycle compr seal gas Instrument List 11-12-15
| CALM |  |  | CALM- |  | CALM-2 | K2002 |  |  |  |  | DGS Process Trouble Common Alarm | Recycle compr seal gas Instrument List 11-12-15
| ESD |  |  | ESD- |  | ESD-100 | K2002 |  |  |  |  | ESD trip Signal From Seal View | Recycle compr seal gas Instrument List 11-12-15
| XL | 210045 | B | XL-210045B |  | HE-131 | K2002 | 4305 | R | 00206B | SHT 7 | Heater Mode Operation Select | Recycle compr seal gas Instrument List 11-12-15 | 210045
| XL | 210045 | A | XL-210045A |  | HE-132 | K2002 | 4305 | R | 00206B | SHT 7 | Heater On/Off | Recycle compr seal gas Instrument List 11-12-15 | 210045
| ST |  |  | ST- |  | ST-100 | K2002 |  |  |  |  | Lube Oil Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 11-12-15
| ST |  |  | ST- |  | ST-101 | K2002 |  |  |  |  | Temperature Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 11-12-15
| Reset |  |  | Reset- |  | Reset | K2002 | [5 empty] | Recycle compr seal gas Instrument List 11-12-15
| Reset |  |  | Reset- |  | Reset | K2002 | [5 empty] | Recycle compr seal gas Instrument List 11-12-15
| Enable |  |  | Enable- |  | Enable | K2002 | [5 empty] | Recycle compr seal gas Instrument List 11-12-15
| XA | 210045 |  | XA-210045 |  | H-130 | K2002 | 4305 | R | 00206B | SHT 7 | Heater common alarm | Recycle compr seal gas Instrument List 11-12-15 | 210045
2015-09-14 | HS | HOME |  | HS-HOME | DELETED PLC POINT |  | K2002 |  |  |  |  | HMI HOME BUTTON | Recycle compr seal gas Instrument List 11-12-15 | HOME
2015-09-14 | HS | FORWARD |  | HS-FORWARD | DELETED PLC POINT |  | K2002 |  |  |  |  | HMI FORWARD BUTTON | Recycle compr seal gas Instrument List 11-12-15 | FORWARD
2015-09-14 | HS | BACK |  | HS-BACK | DELETED PLC POINT |  | K2002 |  |  |  |  | HMI BACK BUTTON | Recycle compr seal gas Instrument List 11-12-15 | BACK
| HS | 210223 |  | HS-210223 |  |  | K2002 |  |  |  |  | reset button | Recycle compr seal gas Instrument List 11-12-15 | 210223
| HS | 210222 |  | HS-210222 |  |  | K2002 |  |  |  |  | ack button | Recycle compr seal gas Instrument List 11-12-15 | 210222
| HS | 210224 |  | HS-210224 |  |  | K2002 |  |  |  |  | test aux lube pump button | Recycle compr seal gas Instrument List 11-12-15 | 210224
| HS | 210225 |  | HS-210225 |  |  | K2002 |  |  |  |  | maintenance mode ss | Recycle compr seal gas Instrument List 11-12-15 | 210225
| XL | 210225 |  | XL-210225 |  |  | K2002 |  |  |  |  | maintenance mode light | Recycle compr seal gas Instrument List 11-12-15 | 210225
| FI | 20101 |  | FI-20101 |  |  | K2002 | 4305 | R | 00201 | SHT 3 | 1st stage recycle compressor disch flow, purchse new indicator and mount on column near the old panel | Recycle compr seal gas Instrument List 11-12-15 | 20101
sd | LIT | 20504 |  | LIT-20504 |  |  | K2002 | 4305 | R | 00201 | SHT 6 | 1st stage high pressure separator, change from level switch to a transmitter | Recycle compr seal gas Instrument List 11-12-15 | 20504
2015-09-23 | PIT | 210245 |  | PIT-210245 | changed tag number from 20414 |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor disch pressure | Recycle compr seal gas Instrument List 11-12-15 | 210245
| TIT | 20015 |  | TIT-20015 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor disch temperature, retag TE-20T024 and add a TIT, demo TSH-20015 | Recycle compr seal gas Instrument List 11-12-15 | 20015
| TSH | 20015 |  | TSH-20015 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | DEMO AND REPLACE WITH TIT-20015 | Recycle compr seal gas Instrument List 11-12-15 | 20015
| TE | 20T024 |  | TE-20T024 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | RETAG AS TE-20015 | Recycle compr seal gas Instrument List 11-12-15 | 20T024
2015-09-23 | PSL | 210234 |  | PSL-210234 | Changed tag prefix from CTA |  | K2002 | 4305 | R | 00201 | SHT 7 | FROM Bently Nevada PANEL PURGE ALARM | Recycle compr seal gas Instrument List 11-12-15 | 210234
sd | CTA | 210230 |  | CTA-210230 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | Bently Nevada common trouble alarm | Recycle compr seal gas Instrument List 11-12-15 | 210230
| XS | 20064 |  | XS-20064 |  |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor run status | Recycle compr seal gas Instrument List 11-12-15 | 20064
sd | XS | 210231 |  | XS-210231 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | FROM BENTLY NEVADA TRIP | Recycle compr seal gas Instrument List 11-12-15 | 210231
2015-11-04 | HS | 210231 |  | HS-210231 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | FROM BENTLY NEVADA TRIP bypass status | Recycle compr seal gas Instrument List 11-12-15 | 210231
2015-09-23 | HS | 20064 |  | HS-20064 | was 20064A, was 20064D, is 20064 with no suffix |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mounted start | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-23 | XL | 20064 | A | XL-20064A | was 20064A, was 20064D, is now 20064A |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mounted start light | Recycle compr seal gas Instrument List 11-12-15 | 20064
| HS | 20064 | AA | HS-20064AA | delete |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor FIELD mounted start | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-23 | HS | 20064 | A | HS-20064A | was 20064B, was 20064A, IS 20064A |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mtd stop | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-23 | XL | 20064 | B | XL-20064B | was 20064B, was 20064A, is now '20064B |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor panel mtd stop light | Recycle compr seal gas Instrument List 11-12-15 | 20064
| HS | 20064 | BA | HS-20064BA | delete |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor FIELD mtd stop | Recycle compr seal gas Instrument List 11-12-15 | 20064
| HS | 210235 |  | HS-210235 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor E stop | Recycle compr seal gas Instrument List 11-12-15 | 210235
| HV | 20610 |  | HV-20610 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | add DVC to valve | Recycle compr seal gas Instrument List 11-12-15 | 20610
| IE | 20643 |  | IE-20643 |  |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor amps | Recycle compr seal gas Instrument List 11-12-15 | 20643
2015-09-23 | PIT | 210244 | A | PIT-210244A | changed tag number from 20410 |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor lube oil pressure | Recycle compr seal gas Instrument List 11-12-15 | 210244
2015-09-23 | PIT | 210244 | B | PIT-210244B | changed tag number from 20410 |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor lube oil pressure | Recycle compr seal gas Instrument List 11-12-15 | 210244
2015-09-23 | XY | 20064 | A | XY-20064A | was 20064A, was 20064D, back to 20064A |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor PLC start | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-23 | XY | 20064 | B | XY-20064B | was 20064B, was 20064A, back to 20064B |  | K2002 | 4305 | R | 00206A | SHT 5 | 1st stage compressor PLC stop | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-23 | XY | 20366 | B1 | XY-20366B1 | tag number was PY-20366, changed from A to B1, changed PLC address |  | K2002 | 4305 | R | 00206A | SHT 3 | Steam supply to lube oil pump spare, need an output from each PLC, REplace 125 VDC sov with 24 vdc sov | Recycle compr seal gas Instrument List 11-12-15 | 20366
sd | PIT | 20366 | A | PIT-20366A |  |  | K2002 | 4305 | R | 00206A | SHT 4 | lube oil pump pressure, change psl to two PIT's | Recycle compr seal gas Instrument List 11-12-15 | 20366
| CTA | 210216 |  | CTA-210216 |  |  | K2002 |  |  |  |  | Recycle 1 PLC power supply alarm | Recycle compr seal gas Instrument List 11-12-15 | 210216
| STROBE | 210218 |  | STROBE-210218 |  |  | K2002 |  |  |  |  | Recycle 1 PLC Beacon | Recycle compr seal gas Instrument List 11-12-15 | 210218
| PSL | 210220 |  | PSL-210220 |  |  | K2002 |  |  |  |  | PLC panel purge alarm | Recycle compr seal gas Instrument List 11-12-15 | 210220
| TIT | 210221 |  | TIT-210221 |  |  | K2002 |  |  |  |  | PLC panel temperature | Recycle compr seal gas Instrument List 11-12-15 | 210221
2015-09-23 | XY | 210241 |  | XY-210241 | added PLC point, changed tag number from 210239A |  | K2002 | 4305 | R | 00206A | SHT 5 | LUBE OIL SHUTOFF VALVE SOV | Recycle compr seal gas Instrument List 11-12-15 | 210241
2015-09-23 | ZSC | 210241 |  | ZSC-210241 | added PLC point, changed tag number from 210239A |  | K2002 | 4305 | R | 00206A | SHT 5 | LUBE OIL SHUTOFF VALVE CLOSED POSITION | Recycle compr seal gas Instrument List 11-12-15 | 210241
2015-09-23 | ZSO | 210241 |  | ZSO-210241 | added PLC point, changed tag number from 210239A |  | K2002 | 4305 | R | 00206A | SHT 5 | LUBE OIL SHUTOFF VALVE OPEN POSITION | Recycle compr seal gas Instrument List 11-12-15 | 210241
2015-09-23 | HS | 210239 |  | HS-210239 | added PLC point, deleted point on 9-14, re used address for HS-20064 on 9-17, removed suffix "AA" from tag number |  | K2002 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP HOA IN AUTO | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | HS | 20366 |  | HS-20366 | added PLC point, deleted point on 9-14, re used address for HS-20064C on 9-17, changed tag number from 210239AB to 20366 |  | K2002 | 4305 | R | 00206A | SHT 3 | SPARE LUBE OIL PUMP, STEAM TURBINE, IN AUTO | Recycle compr seal gas Instrument List 11-12-15 | 20366
2015-09-23 | XS | 210239 |  | XS-210239 | added PLC point, removed "AA" sufix from tag number |  | K2002 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP RUN STATUS | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XY | 210239 | A1 | XY-210239A1 | added PLC point, changed tag suffix from AA to A1 |  | K2002 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP RUN PERMISSIVE | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XY | 210239 | B1 | XY-210239B1 | added PLC point, changed tag suffix from AC to B1 |  | K2002 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP AUTO START | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XY | 20366 | A1 | XY-20366A1 | added PLC point, changed tag number from 210239AD, added PLC address |  | K2002 | 4305 | R | 00206A | SHT 3 | SPARE LUBE OIL PUMP, STEAM TURBINE, PERMISSIVE | Recycle compr seal gas Instrument List 11-12-15 | 20366
2015-09-23 | HS | 20064 | B | HS-20064B | added PLC point' added suffix B |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor DCS console mtd stop | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-17 | HS | 20064 | C | HS-20064C | added PLC point |  | K2002 | 4305 | R | 00201 | SHT 7 | 1st stage compressor DCS soft stop | Recycle compr seal gas Instrument List 11-12-15 | 20064
2015-09-17 | PSH | 20355 |  | PSH-20355 | added PLC point |  | K2002 |  |  |  |  | Lube oil pump steam turbine discharge pressure | Recycle compr seal gas Instrument List 11-12-15 | 20355
2015-10-19 | XY | 210187 | D | XY-210187D | added PLC point, tag number was 210246 |  | K2002 |  |  |  |  | ADS stage 1 Triconex EIV trip | Recycle compr seal gas Instrument List 11-12-15 | 210187
2015-09-23 | XY | 210248 |  | XY-210248 | added PLC point |  | K2002 |  |  |  |  | PLC to DCS Recycle compressor stage 1 tripped | Recycle compr seal gas Instrument List 11-12-15 | 210248
| PIT | 210064 |  | PIT-210064 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2ND Stage Recycle Compressor Suction Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210064
| PIT | 210060 |  | PIT-210060 | C | PIT-100 | K2003 | 4305 | R | 00206B | sht 10 | 1st Stage Recycle Compressor Discharge Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210060
| PDIT | 210062 |  | PDIT-210062 | C | PDIT-120 | K2003 | 4305 | R | 00206B | sht 10 | Cleanpac F diferential pressure | Recycle compr seal gas Instrument List 11-12-15 | 210062
| LIT | 210061 |  | LIT-210061 | C | LIT-120 | K2003 | 4305 | R | 00206B | sht 10 | Cleanpac F Level | Recycle compr seal gas Instrument List 11-12-15 | 210061
| RO | 120 |  | RO-120 |  |  | K2003 | 4305 | R | 00205B | sht 7 | Cleanpac F to 2nd stage recycle Suction | Recycle compr seal gas Instrument List 11-12-15 | 120
| RO | 121 |  | RO-121 |  |  | K2003 | 4305 | R | 00205B | sht 7 | Cleanpac F to 2nd stage recycle Suction | Recycle compr seal gas Instrument List 11-12-15 | 121
| TE | 210063 | A | TE-210063A |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210063
| TC | 210063 |  | TC-210063 |  | TE-100A | K2003 | 4305 | R | 00205B | sht 10 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210063
| TE | 210063 | B | TE-210063B |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210063
| TSHH | 210063 | A | TSHH-210063A |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210063
| TSHH | 210063 | B | TSHH-210063B |  | TE-100A | K2003 | 4305 | R | 00205B | sht 7 | Seal Gas Process Temperature | Recycle compr seal gas Instrument List 11-12-15 | 210063
| TI | 210063 |  | TI-210063 |  | TI-100A | K2003 | 4305 | R | 00205B | sht 7 |  | Recycle compr seal gas Instrument List 11-12-15 | 210063
| XV | 210065 |  | XV-210065 |  |  | K2003 | 4305 | R | 00206B | sht 10 | 2nd Stage Recycle Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 11-12-15 | 210065
| XI | 210065 |  | XI-210065 |  |  | K2003 | 4305 | R | 00206B | sht 10 | 2nd Stage Recycle Ampliflow Solenoid Cycle Feedback | Recycle compr seal gas Instrument List 11-12-15 | 210065
| PCV | 400 |  | PCV-400 |  | PCV-400 | K2003 | 4305 | R | 00205B | sht 7 | 2nd Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 11-12-15 | 400
| PI | 400 |  | PI-400 |  | PI-400 | K2003 | 4305 | R | 00205B | sht 7 | 2nd Stage Recycle Air Supply to Ampliflow Solenoid Cycle Control | Recycle compr seal gas Instrument List 11-12-15 | 400
| PDIT | 210068 |  | PDIT-210068 | C | PDIT-200 | K2003 | 4305 | R | 00206B | sht 11 | Nitrogen Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 11-12-15 | 210068
| PDIT | 210067 |  | PDIT-210067 | C | PDIT-100 | K2003 | 4305 | R | 00206B | sht 11 | Seal Gas Supply Filter Differential Pressure Transmitter | Recycle compr seal gas Instrument List 11-12-15 | 210067
| PIT | 210066 |  | PIT-210066 | C | PIT-300 | K2003 | 4305 | R | 00206B | sht 10 | 2nd Stage Ampliflow process leaksge to flare | Recycle compr seal gas Instrument List 11-12-15 | 210066
| PIT | 210070 |  | PIT-210070 | L | PIT-101 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor Primary Seal Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210070
| FIT | 210069 | A | FIT-210069A | L DCS | FIT-101 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210069
| FE | 210069 | A | FE-210069A |  | FE-101 | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor DE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210069
| FIT | 210069 | B | FIT-210069B | L DCS | FIT-102 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210069
| FE | 210069 | B | FE-210069B |  | FE-102B | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor NDE Primary Seal Gas Flow | Recycle compr seal gas Instrument List 11-12-15 | 210069
| TI | 101 |  | TI-101 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor NDE Primary Seal Gas Temp | Recycle compr seal gas Instrument List 11-12-15 | 101
| PIT | 210073 |  | PIT-210073 | L | PIT-200 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210073
| PCV | 200 |  | PCV-200 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Separation Seal Gas Pressure | Recycle compr seal gas Instrument List 11-12-15 | 200
| RO | 201 |  | RO-201 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DE Separation gas supply | Recycle compr seal gas Instrument List 11-12-15 | 201
| RO | 202 |  | RO-202 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor DNE Separation gas supply | Recycle compr seal gas Instrument List 11-12-15 | 202
| FIT | 210071 |  | FIT-210071 | L | FIT-301 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210071
| FE | 210071 |  | FE-210071 |  | FE-301 | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor DE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210071
| PCV | 300 |  | PCV-300 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 11-12-15 | 300
| PI | 300 |  | PI-300 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 11-12-15 | 300
| RO | 300 |  | RO-300 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | 1st Stage Recycle Compressor Seal gas supply | Recycle compr seal gas Instrument List 11-12-15 | 300
| FIT | 210072 |  | FIT-210072 | L | FIT-302 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210072
| FE | 210072 |  | FE-210072 |  | FE-302 | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor NDE Secondary Seal Gas Supply Flow | Recycle compr seal gas Instrument List 11-12-15 | 210072
| PIT | 210075 |  | PIT-210075 | L | PIT-501 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210075
| FIT | 210077 | A | FIT-210077A |  | FIT-501A | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210077
| FE | 210077 |  | FE-210077 |  | FE-501AB | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210077
| FIT | 210077 | B | FIT-210077B |  | FIT-501B | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210077
| FIT | 210077 | C | FIT-210077C |  | FIT-501C | K2003 | 4305 | R | 00206B | SHT 12 | 2ndt Stage Recycle Compressor NDE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210077
| PIT | 210074 |  | PIT-210074 | L | PIT-502 | K2003 | 4305 | R | 00206B | sht 12 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Pressure | Recycle compr seal gas Instrument List 11-12-15 | 210074
| FIT | 210076 | A | FIT-210076A |  | FIT-502A | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210076
| FE | 210076 |  | FE-210076 |  | FE-502AB | K2003 | 4305 | R | 00200 | SHT 10 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210076
| FIT | 210076 | B | FIT-210076B |  | FIT-502B | K2003 | 4305 | R | 00206B | SHT 12 | 2ndt Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210076
| FIT | 210076 | C | FIT-210076C |  | FIT-502C | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor DE Primary Seal Leakage Flow | Recycle compr seal gas Instrument List 11-12-15 | 210076
| FV | 210069 |  | FV-210069 | L DCS | FCV-100 | K2003 | 4305 | R | 00206B | SHT 12 | 2nd Stage Recycle Compressor Primary Seal Gas Control Valve | Recycle compr seal gas Instrument List 11-12-15 | 210069
| PCV | 100 |  | PCV-100 |  |  | K2003 | 4305 | R | 00200 | SHT 10 | N2 supply to FV-210069 | Recycle compr seal gas Instrument List 11-12-15 | 100
| CALM |  |  | CALM- |  | CALM-1 | K2003 |  |  |  |  | PLC Card and Instrument Failure Common Alarm | Recycle compr seal gas Instrument List 11-12-15
| CALM |  |  | CALM- |  | CALM-2 | K2003 |  |  |  |  | DGS Process Trouble Common Alarm | Recycle compr seal gas Instrument List 11-12-15
| ESD |  |  | ESD- |  | ESD-100 | K2003 |  |  |  |  | ESD trip Signal From Seal View | Recycle compr seal gas Instrument List 11-12-15
| XL | 210063 | B | XL-210063B |  | HE-131 | K2003 | 4305 | R | 00206B | SHT 10 | Heater Mode Operation Select | Recycle compr seal gas Instrument List 11-12-15 | 210063
| XL | 210063 | A | XL-210063A |  | HE-132 | K2003 | 4305 | R | 00206B | SHT 10 | Heater On/Off | Recycle compr seal gas Instrument List 11-12-15 | 210063
| ST |  |  | ST- |  | ST-100 | K2003 |  |  |  |  | Lube Oil Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 11-12-15
| ST |  |  | ST- |  | ST-101 | K2003 |  |  |  |  | Temperature Start Permissive Signal from Seal View | Recycle compr seal gas Instrument List 11-12-15
| Reset |  |  | Reset- |  | Reset | K2003 | [5 empty] | Recycle compr seal gas Instrument List 11-12-15
| Reset |  |  | Reset- |  | Reset | K2003 | [5 empty] | Recycle compr seal gas Instrument List 11-12-15
| Enable |  |  | Enable- |  | Enable | K2003 | [5 empty] | Recycle compr seal gas Instrument List 11-12-15
| XA | 210063 |  | XA-210063 |  | H-130 | K2003 | 4305 | R | 00206B | SHT 10 | Heater common alarm | Recycle compr seal gas Instrument List 11-12-15 | 210063
2015-09-17 | HS | HOME |  | HS-HOME | DELETED PLC POINT |  | K2003 |  |  |  |  | HMI HOME BUTTON | Recycle compr seal gas Instrument List 11-12-15 | HOME
2015-09-17 | HS | FORWARD |  | HS-FORWARD | DELETED PLC POINT |  | K2003 |  |  |  |  | HMI FORWARD BUTTON | Recycle compr seal gas Instrument List 11-12-15 | FORWARD
2015-09-17 | HS | BACK |  | HS-BACK | DELETED PLC POINT |  | K2003 |  |  |  |  | HMI BACK BUTTON | Recycle compr seal gas Instrument List 11-12-15 | BACK
2015-09-17 | HS | 210227 |  | HS-210227 | DELETED PLC POINT, point is still in scope |  | K2003 |  |  |  |  | reset button | Recycle compr seal gas Instrument List 11-12-15 | 210227
2015-09-17 | HS | 210226 |  | HS-210226 | DELETED PLC POINT, point is still in scope |  | K2003 |  |  |  |  | ack button | Recycle compr seal gas Instrument List 11-12-15 | 210226
2015-09-01 | HS | 210240 |  | HS-210240 | was tag number 210028 |  | K2003 |  |  |  |  | testAUX PUMP button | Recycle compr seal gas Instrument List 11-12-15 | 210240
| HS | 210229 |  | HS-210229 |  |  | K2003 |  |  |  |  | maintenance mode ss | Recycle compr seal gas Instrument List 11-12-15 | 210229
| XL | 210229 |  | XL-210229 |  |  | K2003 |  |  |  |  | maintenance mode light | Recycle compr seal gas Instrument List 11-12-15 | 210229
| FI | 20108 |  | FI-20108 |  |  | K2003 |  |  |  |  | 2nd stage recycle compressor disch flow, purchse new indicator and mount on column near the old panel | Recycle compr seal gas Instrument List 11-12-15 | 20108
2015-09-01 | LIT | 20594 |  | LIT-20594 | tag number was LIT-20529 |  | K2003 | 4305 | R | 00202 | SHT 6 | 2nd stage high pressure separator, change from level switch to a transmitter | Recycle compr seal gas Instrument List 11-12-15 | 20594
2015-10-19 | PIT | 210250 |  | PIT-210250 | tag number was PIT-20416 |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor disch pressure | Recycle compr seal gas Instrument List 11-12-15 | 210250
| TIT | 20025 |  | TIT-20025 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor disch temperature, retag TE-20T046 and add a TIT, demo TSH-20025 | Recycle compr seal gas Instrument List 11-12-15 | 20025
| TSH | 20025 |  | TSH-20025 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | DEMO AND REPLACE WITH TIT-20025 | Recycle compr seal gas Instrument List 11-12-15 | 20025
| TE | 20T046 |  | TE-20T046 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | RETAG AS TE-20025 | Recycle compr seal gas Instrument List 11-12-15 | 20T046
sd | XS | 210233 |  | XS-210233 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FROM BENTLY NEVADA TRIP | Recycle compr seal gas Instrument List 11-12-15 | 210233
2015-11-04 | HS | 210233 |  | HS-210233 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FROM BENTLY NEVADA TRIP bypass status | Recycle compr seal gas Instrument List 11-12-15 | 210233
sd | CTA | 210232 |  | CTA-210232 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | Bently Nevada common trouble alarm | Recycle compr seal gas Instrument List 11-12-15 | 210232
| XS | 20065 |  | XS-20065 |  |  | K2003 | 4305 | R | 00206 | SHT 3 | 2nd stage compressor run status | Recycle compr seal gas Instrument List 11-12-15 | 20065
sd | TSH | 20026 |  | TSH-20026 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | FROM BENTLY NEVADA | Recycle compr seal gas Instrument List 11-12-15 | 20026
2015-09-23 | HS | 20065 |  | HS-20065 | was 20065A, was 20065D, is 20065 with no suffix |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mounted start | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-23 | XL | 20065 | A | XL-20065A | was 20065A, was 20065D, is now 20065A |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mounted start light | Recycle compr seal gas Instrument List 11-12-15 | 20065
sd | HS | 20065 | AA | HS-20065AA | delete |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FIELD mounted start | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-23 | HS | 20065 | A | HS-20065A | was 20065B, was 20065A, IS 20065A |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mtd stop | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-23 | XL | 20065 | B | XL-20065B | was 20065B, was 20065A, is now '20065B |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor panel mtd stop light | Recycle compr seal gas Instrument List 11-12-15 | 20065
sd | HS | 20065 | BA | HS-20065BA | delete |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor FIELD mtd stop | Recycle compr seal gas Instrument List 11-12-15 | 20065
sd | HS | 210236 |  | HS-210236 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor E stop | Recycle compr seal gas Instrument List 11-12-15 | 210236
| HV | 20608 |  | HV-20608 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | add DVC to valve | Recycle compr seal gas Instrument List 11-12-15 | 20608
| IE | 20616 |  | IE-20616 |  |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor amps | Recycle compr seal gas Instrument List 11-12-15 | 20616
sd | PIT | 20317 | A | PIT-20317A |  |  | K2003 | 4305 | R | 00206A | SHT 3 | 2nd stage compressor lube oil pressure | Recycle compr seal gas Instrument List 11-12-15 | 20317
sd | PIT | 20317 | B | PIT-20317B |  |  | K2003 | 4305 | R | 00206A | SHT 3 | 2nd stage compressor lube oil pressure | Recycle compr seal gas Instrument List 11-12-15 | 20317
2015-09-23 | XY | 20065 | A | XY-20065A | was 20065A, was 20065D, back to 20065A |  | K2003 | 4305 | R | 00206 | SHT 3 | 2nd stage compressor PLC start | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-23 | XY | 20065 | B | XY-20065B | was 20065B, was 20065A, back to 20065B |  | K2003 | 4305 | R | 00206 | SHT 3 | 2nd stage compressor PLC stop | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-23 | XY | 20366 | B2 | XY-20366B2 | tag number was PY-20366, changed from B to B2, changed PLC address |  | K2003 | 4305 | R | 00206A | SHT 3 | Steam supply to lube oil pump spare, need an output from each PLC, REplace 125 VDC sov with 24 vdc sov | Recycle compr seal gas Instrument List 11-12-15 | 20366
| PSH | 20355 |  | PSH-20355 |  |  | K2003 | 4305 | R | 00206A | SHT 3 | lube oil spare pump disch pressure, to only one of the PLC's | Recycle compr seal gas Instrument List 11-12-15 | 20355
2015-10-19 | PDIT | 210247 |  | PDIT-210247 | Tag number was 20352 |  | K2003 | 4305 | R | 00206A | SHT 4 | lube oil filter diff pressure, to only one of the PLC's | Recycle compr seal gas Instrument List 11-12-15 | 210247
2015-10-19 | TSH | 210246 |  | TSH-210246 | Tag number was 20028 |  | K2003 | 4305 | R | 00206A | SHT 4 | lube oil filter diff temperature, to only one of the PLC's | Recycle compr seal gas Instrument List 11-12-15 | 210246
sd | PIT | 20366 | B | PIT-20366B |  |  | K2003 | 4305 | R | 00206A | SHT 4 | lube oil pump pressure, change psl to two PIT's | Recycle compr seal gas Instrument List 11-12-15 | 20366
| CTA | 210217 |  | CTA-210217 |  |  | K2003 |  |  |  |  | Recycle 2 PLC power supply alarm | Recycle compr seal gas Instrument List 11-12-15 | 210217
| STROBE | 210219 |  | STROBE-210219 |  |  | K2003 |  |  |  |  | Recycle 2 PLC Beacon | Recycle compr seal gas Instrument List 11-12-15 | 210219
2015-09-23 | XY | 210242 |  | XY-210242 | added PLC point, changed tag number from 210239B |  | K2003 | 4305 | R | 00206A | SHT 3 | LUBE OIL SHUTOFF VALVE SOV | Recycle compr seal gas Instrument List 11-12-15 | 210242
2015-09-23 | ZSC | 210242 |  | ZSC-210242 | added PLC point |  | K2003 | 4305 | R | 00206A | SHT 3 | LUBE OIL SHUTOFF VALVE CLOSED POSITION | Recycle compr seal gas Instrument List 11-12-15 | 210242
2015-09-23 | ZSO | 210242 |  | ZSO-210242 | added PLC point |  | K2003 | 4305 | R | 00206A | SHT 3 | LUBE OIL SHUTOFF VALVE OPEN POSITION | Recycle compr seal gas Instrument List 11-12-15 | 210242
2015-09-23 | HS | 210239 | BA | HS-210239BA | added PLC point, deleted point on 9-14, re used address for HS-20065 on 9-17, deleted tag |  | K2003 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP HOA IN AUTO | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | HS | 210239 | BB | HS-210239BB | added PLC point, deleted point on 9-14, re used address for HS-20065C on 9-17, deleted tag |  | K2003 | 4305 | R | 00206A | SHT 3 | SPARE LUBE OIL PUMP, STEAM TURBINE, IN AUTO | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XS | 210239 |  | XS-210239 | added PLC point, removed "BA" sufix from tag number |  | K2003 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP RUN STATUS | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XY | 210239 | A2 | XY-210239A2 | added PLC point, changed tag suffix from BA to A2 |  | K2003 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP RUN PERMISSIVE | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XY | 210239 | B2 | XY-210239B2 | added PLC point, changed tag suffix from BC to B2 |  | K2003 | 4305 | R | 00206A | SHT 4 | LUBE OIL PUMP AUTO START | Recycle compr seal gas Instrument List 11-12-15 | 210239
2015-09-23 | XY | 20366 | A2 | XY-20366A2 | added PLC point, changed tag number from 210239BD, added PLC address |  | K2003 | 4305 | R | 00206A | SHT 3 | SPARE LUBE OIL PUMP, STEAM TURBINE, PERMISSIVE | Recycle compr seal gas Instrument List 11-12-15 | 20366
2015-09-23 | HS | 20065 | B | HS-20065B | added PLC point' added suffix B |  | K2003 | 4305 | R | 00202 | SHT 7 | 2nd stage compressor DCS console mtd stop | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-17 | HS | 20065 | C | HS-20065C | added PLC point |  | K2003 | 4305 | R | 00202 | SHT 7 | 2ndt stage compressor DCS soft stop | Recycle compr seal gas Instrument List 11-12-15 | 20065
2015-09-17 | PSH | 20355 |  | PSH-20355 | added PLC point |  | K2003 |  |  |  |  | Lube oil pump steam turbine discharge pressure | Recycle compr seal gas Instrument List 11-12-15 | 20355
2015-10-19 | XY | 210199 | D | XY-210199D | added PLC point, tag number was 210247 |  | K2003 |  |  |  |  | ADS stage 2 Triconex EIV trip | Recycle compr seal gas Instrument List 11-12-15 | 210199
2015-09-23 | XY | 210249 |  | XY-210249 | added PLC point |  | K2003 |  |  |  |  | PLC to DCS Recycle compressor stage 2 tripped | Recycle compr seal gas Instrument List 11-12-15 | 210249
| LIT | 20541 |  | LIT-20541 |  |  | DEMO | 4305 | R | 00206B | SHT 3 | 2ND STAGE SEAL OIL TANK | Recycle compr seal gas Instrument List 11-12-15 | 20541
| LIT | 20542 |  | LIT-20542 |  |  | DEMO | 4305 | R | 00206B | SHT 6 | 1ST STAGE SEAL OIL TANK | Recycle compr seal gas Instrument List 11-12-15 | 20542
| PSH | 20389 |  | PSH-20389 |  |  | DEMO | 4305 | R | 00206B | SHT 4 | 1ST AND 2ND STAGE REC COMP SP SO | Recycle compr seal gas Instrument List 11-12-15 | 20389
| PDIT | 20383 |  | PDIT-20383 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL DIFFERENTIALS | Recycle compr seal gas Instrument List 11-12-15 | 20383
| PIT | 20390 |  | PIT-20390 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL 2ND STAGE | Recycle compr seal gas Instrument List 11-12-15 | 20390
| PIT | 20391 |  | PIT-20391 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL 1ST STAGE | Recycle compr seal gas Instrument List 11-12-15 | 20391
| PDIT | 20385 |  | PDIT-20385 |  |  | DEMO | 4305 | R | 00206B | SHT 5 | SEAL OIL FILTER DIFFERENTIAL | Recycle compr seal gas Instrument List 11-12-15 | 20385
| PDIT | 20384 |  | PDIT-20384 |  |  | DEMO | 4305 | R | 00206B | SHT 6 | SEAL OIL 1ST STAGE | Recycle compr seal gas Instrument List 11-12-15 | 20384
| FI | 20101 |  | FI-20101 |  |  | REWIRE | 4305 | R | 00201 | SHT 3 | 1ST STAGE FEED | Recycle compr seal gas Instrument List 11-12-15 | 20101
| FI | 20108 |  | FI-20108 |  |  | REWIRE | 4305 | R | 00202 | SHT 3 | 2ND STAGE FEED | Recycle compr seal gas Instrument List 11-12-15 | 20108